## Blank Task Inventory Template
Task Inventory Template Designed by Spreadsheet Daddy
[Company Name] [Address]
Prepared by | Date Prepared | Reviewed by | Date reviewed | Notes
Task Identification |  |  | Assignment & Responsibility |  | Scheduling & Timing |  |  | Priority & Status |  |  | Notes
Task ID | Task Description | Category | Assigned To | Dependencies | Start Date | Due Date | Estimated Time | Importance | Status | Completion Percentage

## Task Inventory Template Example
Task Inventory Template Designed by Spreadsheet Daddy
Peak Performance Solutions 2150 Summit Avenue, Chicago, IL 60616, USA
Prepared by | Date Prepared | Reviewed by | Date reviewed | Notes
A. Johnson | 2025-10-07 | M. Smith | 2025-10-07 | Example task inventory for team project tracking
Task Identification |  |  | Assignment & Responsibility |  | Scheduling & Timing |  |  | Priority & Status |  |  | Notes
Task ID | Task Description | Category | Assigned To | Dependencies | Start Date | Due Date | Estimated Time | Importance | Status | Completion Percentage
T001 | Design project logo | Design | L. Carter | None | 2025-10-07 | 2025-10-10 | 8h | High | In Progress | 50% | Initial sketches reviewed
T002 | Write project proposal | Documentation | S. Patel | None | 2025-10-07 | 2025-10-12 | 12h | High | Not Started | 0% | Needs manager input
T003 | Set up project timeline | Planning | J. Lee | T002 | 2025-10-09 | 2025-10-11 | 4h | Medium | Not Started | 0% | Use Gantt chart template
T004 | Conduct market research | Research | R. Gomez | None | 2025-10-07 | 2025-10-15 | 20h | High | In Progress | 30% | Focus on competitors
T005 | Draft social media plan | Marketing | A. Nguyen | T004 | 2025-10-13 | 2025-10-17 | 6h | Medium | Not Started | 0% | Include content calendar
T006 | Review budget proposal | Finance | M. Smith | T002 | 2025-10-10 | 2025-10-12 | 3h | High | Not Started | 0% | Check allocation for marketing
T007 | Develop website homepage | IT | K. Brown | T001 | 2025-10-11 | 2025-10-20 | 25h | High | Not Started | 0% | Use approved brand colors
T008 | Test website functionality | Quality Check | P. White | T007 | 2025-10-21 | 2025-10-25 | 15h | High | Not Started | 0% | Include mobile responsiveness
T009 | Prepare team meeting agenda | Administrative | L. Carter | None | 2025-10-08 | 2025-10-09 | 2h | Medium | Completed | 100% | Agenda sent to all team members
T010 | Conduct team meeting | Administrative | S. Patel | T009 | 2025-10-09 | 2025-10-09 | 1h | Medium | Completed | 100% | Meeting notes documented
T011 | Create training materials | Training | R. Gomez | None | 2025-10-07 | 2025-10-14 | 18h | Medium | In Progress | 40% | Focus on onboarding new hires
T012 | Upload project files to server | IT | J. Lee | None | 2025-10-07 | 2025-10-08 | 2h | High | Completed | 100% | Confirmed access for all team members
T013 | Review legal compliance | Legal | M. Smith | T002 | 2025-10-12 | 2025-10-16 | 10h | High | Not Started | 0% | Include contract review
T014 | Schedule client meeting | Communication | A. Nguyen | T002 | 2025-10-10 | 2025-10-12 | 1h | High | Not Started | 0% | Coordinate with client calendar
T015 | Prepare presentation slides | Design | L. Carter | T001 | 2025-10-14 | 2025-10-17 | 6h | Medium | Not Started | 0% | Use brand guidelines
T016 | Conduct product testing | Quality Check | P. White | T008 | 2025-10-26 | 2025-10-30 | 20h | High | Not Started | 0% | Record bugs and feedback
T017 | Launch marketing campaign | Marketing | A. Nguyen | T005 | 2025-10-18 | 2025-10-25 | 15h | High | Not Started | 0% | Schedule posts in advance
T018 | Analyze campaign results | Marketing | S. Patel | T017 | 2025-10-26 | 2025-10-30 | 10h | Medium | Not Started | 0% | Focus on engagement metrics
T019 | Update project documentation | Documentation | J. Lee | T011 | 2025-10-15 | 2025-10-20 | 8h | Medium | Not Started | 0% | Include latest QA feedback
T020 | Close project & archive files | Administrative | M. Smith | All tasks | 2025-10-31 | 2025-10-31 | 4h | High | Not Started | 0% | Ensure backup copies saved