## Blank Bug Tracker Template
Bug Tracker Template Designed by Spreadsheet Daddy
Bug ID | Date Reported | Reporter | Description | Priority | Assigned To | Status | Resolution | Due Date | Category | Notes

## Bug Tracker Template Example
Bug Tracker Template Designed by Spreadsheet Daddy
Bug ID | Date Reported | Reporter | Description | Priority | Assigned To | Status | Resolution | Due Date | Category | Notes
BUG-001 | 2026-01-05 | Alice | Login page shows error 500 | Critical | John | Open |  | 2026-01-07 | Authentication | Happens after password reset
BUG-002 | 2026-01-05 | Bob | Forgot password email not sent | High | Emma | In Progress |  | 2026-01-08 | Email | Only affects Gmail users
BUG-003 | 2026-01-06 | Charlie | Profile picture upload fails | Medium | Mike | Resolved | Fixed image size limit | 2026-01-06 | UI | Only PNG files affected
BUG-004 | 2026-01-06 | Alice | Search results pagination broken | High | Sarah | Open |  | 2026-01-10 | Search | Appears on Chrome only
BUG-005 | 2026-01-06 | David | Dashboard charts not loading | Critical | John | Open |  | 2026-01-09 | Analytics | Network request times out
BUG-006 | 2026-01-07 | Emma | Mobile menu overlaps content | Medium | Mike | In Progress |  | 2026-01-12 | UI | iPhone Safari only
BUG-007 | 2026-01-07 | Frank | Notification emails duplicated | Low | Sarah | Resolved | Fixed duplicate trigger | 2026-01-07 | Email | Rare case on multiple devices
BUG-008 | 2026-01-07 | Bob | Error 403 on admin page | High | John | Open |  | 2026-01-11 | Permissions | Happens after role update
BUG-009 | 2026-01-08 | Charlie | Slow load time for reports | Medium | Mike | In Progress |  | 2026-01-15 | Performance | Large data sets only
BUG-010 | 2026-01-08 | Alice | Button hover effect not working | Low | Sarah | Resolved | Fixed CSS | 2026-01-08 | UI | Minor cosmetic issue
BUG-011 | 2026-01-09 | David | Unable to export CSV | High | John | Open |  | 2026-01-13 | Reports | Only affects Firefox
BUG-012 | 2026-01-09 | Emma | Password strength meter inaccurate | Medium | Mike | In Progress |  | 2026-01-14 | Security | Sometimes shows weak password as strong
BUG-013 | 2026-01-10 | Frank | Chat messages not updating in real-time | High | Sarah | Open |  | 2026-01-15 | Chat | Only for group chats
BUG-014 | 2026-01-10 | Bob | Tooltip text cutoff on hover | Low | Mike | Resolved | Adjusted tooltip CSS | 2026-01-10 | UI | Minor visual issue
BUG-015 | 2026-01-11 | Alice | Session timeout too short | Medium | John | In Progress |  | 2026-01-17 | Security | Users logged out unexpectedly