## Blank Event Planning Template
Event Planning Template Designed by Spreadsheet Daddy
Event Name |  | Date | Time | Location | Organizer | Target Number of Guests
Task & Timeline Planner |  |  |  |  | Budget & Expenses Tracker |  |  |  | Guest List
Task Name | Assigned To |  | Priority | Status | Category | Planned Cost | Actual Cost | Payment Status | Guest Name | Email | Phone | Invitation Sent | RSVP Status
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Event Planning Template Example
Event Planning Template Designed by Spreadsheet Daddy
Event Name |  | Date | Time | Location | Organizer | Target Number of Guests
Annual Marketing Meetup |  | 2026-03-15 | 10:00 AM – 4:00 PM | Grandview Conference Hall | Sarah Johnson | 50
Task & Timeline Planner |  |  |  |  | Budget & Expenses Tracker |  |  |  | Guest List
Task Name | Assigned To |  | Priority | Status | Category | Planned Cost | Actual Cost | Payment Status | Guest Name | Email | Phone | Invitation Sent | RSVP Status
Book Venue | Sarah Johnson |  | High | Completed | Venue | 1500 | 1500 | Paid | Alice Brown | alice.brown@email.com | 555-1234 | TRUE | Attending
Confirm Speakers | John Lee |  | High | In Progress | Catering | 2000 | 1950 | Paid | Mark Davis | mark.davis@email.com | 555-5678 | TRUE | Not Attending
Send Invitations | Maria Gomez |  | Medium | In Progress | AV Equipment | 500 | 500 | Paid | Sophie Lee | sophie.lee@email.com | 555-8765 | TRUE | Maybe
Arrange Catering | Daniel Smith |  | High | In Progress | Decorations | 300 | 280 | Paid | James Carter | james.carter@email.com | 555-4321 | TRUE | Attending
Prepare Event Schedule | Sarah Johnson |  | Medium | Pending | Printing Materials | 150 | 160 | Paid | Emily Nguyen | emily.nguyen@email.com | 555-9876 | TRUE | Maybe
Set Up AV Equipment | Tech Team |  | Medium | In Progress | Marketing / Promotion | 400 | 350 | Paid | Michael Chen | michael.chen@email.com | 555-3456 | FALSE | Not Attending
Print Name Badges | Maria Gomez |  | Low | In Progress |  |  |  |  | Olivia White | olivia.white@email.com | 555-6543 | TRUE | Attending
Arrange Decorations | Emily Wong |  | Low | In Progress |  |  |  |  | Daniel Kim | daniel.kim@email.com | 555-2468 | TRUE | Not Attending
[9 empty] | Hannah Patel | hannah.patel@email.com | 555-1357 | TRUE | Attending
[9 empty] | Ryan Lopez | ryan.lopez@email.com | 555-9753 | TRUE | Maybe
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE