## Blank Goal Setting Template
Goal Setting Template Designed by Spreadsheet Daddy
Actions | Priority | Potential Obstacles | Assigned To | Start Date | End Date | Status | Notes
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]

## Goal Setting Template Example
Goal Setting Template Designed by Spreadsheet Daddy
Actions | Priority | Potential Obstacles | Assigned To | Start Date | End Date | Status | Notes
Launch Company Website
Define website requirements | High | Unclear scope | Marketing Team | 2026-02-01 | 2026-02-03 | Completed | Requirements approved
Design homepage & layout | High | Design revisions | Designer | 2026-02-04 | 2026-02-10 | In Progress | Waiting for feedback
Write website content | Medium | Content delays | Content Writer | 2026-02-08 | 2026-02-15 | Not Started | Draft outline ready
Website development | High | Technical issues | Developer | 2026-02-12 | 2026-02-25 | Not Started | CMS selected
Testing & launch | High | Bug fixes | QA Team | 2026-02-26 | 2026-03-01 | Not Started
Increase Monthly Sales by 15%
Analyze current sales data | High | Incomplete data | Sales Manager | 2026-02-01 | 2026-02-03 | Completed | Key gaps identified
Launch promotional campaign | High | Budget limits | Marketing Team | 2026-02-05 | 2026-02-20 | In Progress | Social ads running
Upsell existing customers | Medium | Low response rate | Sales Team | 2026-02-05 | 2026-02-28 | On Track | Scripts updated
Track weekly performance | Medium | Reporting delays | Analyst | 2026-02-07 | 2026-02-28 | On Track | Dashboard created
Improve Team Productivity
Review current workflows | High | Resistance to change | Team Lead | 2026-02-01 | 2026-02-05 | Completed | Bottlenecks identified
Implement task management tool | High | Learning curve | Operations | 2026-02-06 | 2026-02-10 | In Progress | Tool selected
Team training session | Medium | Scheduling conflicts | HR | 2026-02-11 | 2026-02-15 | Not Started | Trainer booked
Measure productivity metrics | Medium | Data accuracy | Team Lead | 2026-02-16 | 2026-02-28 | Not Started | Baseline pending
Complete Online Certification
Enroll in course | High | Payment issues | Self | 2026-02-01 | 2026-02-01 | Completed | Access granted
Complete Module 1–3 | High | Time management | Self | 2026-02-02 | 2026-02-10 | In Progress | Module 2 done
Complete final assessment | High | Exam difficulty | Self | 2026-02-11 | 2026-02-15 | Not Started | Revision needed
Download certificate | Low | Platform delay | Self | 2026-02-16 | 2026-02-16 | Not Started
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]
[Goal]