## Blank Home Renovation Budget Te
Home Renovation Budget Template Designed by Spreadsheet Daddy
Budget | Remaining Budget
0
Item | Description | QTY | Estimated Cost | Actual Cost | Difference | Payment Status | Notes
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0

## Home Renovation Budget Template
Home Renovation Budget Template Designed by Spreadsheet Daddy
Budget | Remaining Budget
50000 | 21740
Item | Description | QTY | Estimated Cost | Actual Cost | Difference | Payment Status | Notes
Kitchen
Cabinets | Custom kitchen cabinets | 1 | 6500 | 6700 | -200 | Paid | Price increase
Countertops | Quartz countertops | 1 | 3200 | 3100 | 100 | Paid | Discount applied
Appliances | Oven, fridge, dishwasher | 3 | 4500 | 4450 | 50 | Paid | Bundle deal
Plumbing | Sink & faucet install | 1 | 850 | 900 | -50 | Paid | Extra fittings
Lighting | Under-cabinet lighting | 6 | 600 | 580 | 20 | Paid
Flooring | Kitchen tile flooring | 1 | 1200 | 1300 | -100 | Paid | Labor increase
0
0
0
Total |  |  | 16850 | 17030 | -180
Bathroom
Shower | Walk-in shower | 1 | 2400 | 2350 | 50 | Paid
Toilet | New toilet | 1 | 450 | 480 | -30 | Paid | Model upgrade
Vanity | Sink & vanity unit | 1 | 1200 | 1150 | 50 | Paid
Tiles | Wall & floor tiles | 1 | 1600 | 1700 | -100 | Paid | Extra tiles
Plumbing | Pipe replacement | 1 | 900 | 850 | 50 | Paid
0
0
0
0
Total |  |  | 6550 | 6530 | 20
Living Room
Flooring | Laminate flooring | 1 | 1800 | 1750 | 50 | Paid
Paint | Walls & ceiling | 1 | 600 | 620 | -20 | Paid | Extra paint
Lighting | Ceiling fixtures | 2 | 400 | 390 | 10 | Paid
Curtains | Custom curtains | 1 | 900 | 880 | 20 | Paid
Electrical | New outlets | 1 | 350 | 360 | -10 | Paid
Shelving | Built-in shelves | 1 | 750 | 700 | 50 | Paid
0
0
0
Total |  |  | 4800 | 4700 | 100
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0
[Category]
0
0
0
0
0
0
0
0
0
Total |  |  | 0 | 0 | 0