## Blank Project Management Templa
Project Management Template Designed by Spreadsheet Daddy
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Notes

## Project Management Template Exa
Project Management Template Designed by Spreadsheet Daddy
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | Priority | Notes
PM-01 | Define project scope | Alex Brown | 2026-08-01 | 2026-08-03 | Completed | High | Approved by stakeholders
PM-02 | Create project timeline | Maria Lopez | 2026-08-02 | 2026-08-05 | Completed | High | Shared with team
PM-03 | Assign team roles | John Smith | 2026-08-03 | 2026-08-04 | Completed | Medium | Roles confirmed
PM-04 | Set up project workspace | Emma Wilson | 2026-08-04 | 2026-08-06 | Completed | Medium | Google Drive folders created
PM-05 | Develop budget plan | Daniel Kim | 2026-08-05 | 2026-08-08 | In Progress | High | Awaiting final costs
PM-06 | Identify project risks | Sophia Lee | 2026-08-06 | 2026-08-09 | In Progress | Medium | Risk log started
PM-07 | Stakeholder kickoff meeting | Alex Brown | 2026-08-07 | 2026-08-07 | Completed | High | Meeting notes recorded
PM-08 | Create communication plan | Maria Lopez | 2026-08-08 | 2026-08-10 | Not Started | Medium | Draft outline ready
PM-09 | Gather requirements | John Smith | 2026-08-09 | 2026-08-14 | In Progress | High | Interviews ongoing
PM-10 | Design initial mockups | Emma Wilson | 2026-08-11 | 2026-08-16 | Not Started | Medium | Awaiting requirements
PM-11 | Review legal compliance | Daniel Kim | 2026-08-12 | 2026-08-15 | Not Started | High | External review needed
PM-12 | Develop prototype | Sophia Lee | 2026-08-15 | 2026-08-25 | Not Started | High | Depends on mockups
PM-13 | Internal testing | QA Team | 2026-08-26 | 2026-08-30 | Not Started | Medium | Test cases pending
PM-14 | Final stakeholder review | Alex Brown | 2026-08-31 | 2026-08-31 | Not Started | High | Presentation required
PM-15 | Project closure & report | Maria Lopez | 2026-09-01 | 2026-09-03 | Not Started | Low | Lessons learned