## Blank RACI Template
RACI Template Designed by Spreadsheet Daddy
Project Title | Project Manager
Task | Priority | Status | Due Date | Responsible | Accountable | Consulted | Informed | Notes

## RACI Template Example
RACI Template Designed by Spreadsheet Daddy
Project Title | Project Manager
Website Redesign Project | Sarah Johnson
Task | Priority | Status | Due Date | Responsible | Accountable | Consulted | Informed | Notes
Project kickoff meeting | High | Completed | 2026-01-05 | Sarah Johnson | Sarah Johnson | Stakeholders | Team | Agenda and minutes shared
Gather requirements | High | Completed | 2026-01-08 | Emily Clark | Sarah Johnson | Client, UX Team | Dev Team | Approved requirements doc
Create wireframes | Medium | Completed | 2026-01-12 | Daniel Lee | Sarah Johnson | UX Team | Client | Initial layout approved
Design UI mockups | High | In Progress | 2026-01-18 | Olivia Brown | Sarah Johnson | Marketing | Dev Team | Waiting for brand feedback
Content audit | Medium | Completed | 2026-01-10 | Michael Davis | Sarah Johnson | SEO Specialist | Client | Content gaps identified
Front-end development | High | In Progress | 2026-01-25 | James Wilson | Sarah Johnson | Designer | Client | Using React framework
Back-end integration | High | Not Started | 2026-01-30 | Laura Martinez | Sarah Johnson | Dev Team | Client | Depends on API readiness
Quality assurance testing | Medium | Not Started | 2026-02-03 | Kevin Thompson | Sarah Johnson | Dev Team | Stakeholders | Test cases prepared
Client review & feedback | High | Not Started | 2026-02-07 | Client Rep | Sarah Johnson | Design & Dev | Team | Review meeting scheduled
Final launch | High | Not Started | 2026-02-10 | Sarah Johnson | Sarah Johnson | IT Support | All Stakeholders | Rollback plan required