## Blank RAID Log Template
RAID Log Template Designed by Spreadsheet Daddy
ID | Category | Description | Impact | Priority | Owner | Status | Mitigation | Due date | Notes

## RAID Log Template Example
RAID Log Template Designed by Spreadsheet Daddy
ID | Category | Description | Impact | Priority | Owner | Status | Mitigation | Due date | Notes
1 | Risk | Supplier delivery may be delayed | High | High | Project Manager | Open | Confirm delivery dates weekly | 2026-02-10 | Backup supplier identified
2 | Assumption | All team members are available full-time | Medium | Medium | Team Lead | In Progress | Monitor workload weekly | 2026-02-05 | May change during holidays
3 | Issue | Website testing is behind schedule | High | High | QA Lead | In Progress | Add extra testing resources | 2026-02-02 | Two days behind
4 | Dependency | Final design approval from client | High | High | Client Manager | Open | Send reminder email | 2026-02-01 | Blocking development
5 | Risk | Budget may exceed initial estimate | High | Medium | Finance Manager | Open | Review costs biweekly | 2026-02-15 | Inflation impact
6 | Assumption | Software licenses will be approved | Medium | Medium | IT Manager | Resolved | Prepare alternative tools | 2026-02-03 | Waiting for confirmation
7 | Issue | Key team member is on sick leave | Medium | Medium | HR Manager | Open | Reassign tasks temporarily | 2026-02-04 | Expected return next week
8 | Dependency | Data required from external partner | High | High | Operations Lead | Open | Escalate to partner management | 2026-02-06 | Data format unclear
9 | Risk | System integration may fail | High | High | Technical Lead | Open | Run early integration tests | 2026-02-08 | Complex APIs
10 | Assumption | Stakeholders will respond within 48 hours | Low | Low | Project Manager | In Progress | Follow up after 2 days | 2026-02-07 | Usually responsive
11 | Issue | Training materials are incomplete | Medium | Medium | Training Coordinator | In Progress | Assign content writer | 2026-02-05 | Draft version ready
12 | Dependency | Approval from legal department | Medium | Medium | Legal Advisor | Open | Schedule review meeting | 2026-02-09 | Required before launch
13 | Risk | New regulations may affect project scope | High | Medium | Compliance Officer | Open | Monitor regulatory updates | 2026-02-20 | No changes yet
14 | Issue | Incorrect data entered in report | Low | Low | Data Analyst | Resolved | Corrected and reviewed | 2026-01-30 | No further impact
15 | Dependency | Hardware delivery for testing | Medium | Medium | Procurement Lead | Open | Track shipment daily | 2026-02-07 | Shipment in transit