## Blank Risk Register Template
Risk Register Template Designed by Spreadsheet Daddy
Risk ID | Risk Description | Category | Likelihood (1-5) | Severity (1-5) | Risk Score | Mitigation | Responsible Person | Status | Date Identified | Review Date | Notes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Risk Register Template Example
Risk Register Template Designed by Spreadsheet Daddy
Risk ID | Risk Description | Category | Likelihood (1-5) | Severity (1-5) | Risk Score | Mitigation | Responsible Person | Status | Date Identified | Review Date | Notes
R-01 | Delay in supplier delivery | Operational | 3 | 4 | 12 | Identify backup suppliers | Operations Manager | Open | 2026-01-05 | 2026-02-05 | Supplier located overseas
R-02 | Budget overrun | Financial | 2 | 5 | 10 | Track expenses weekly | Finance Manager | In Progress | 2026-01-06 | 2026-02-06 | Costs higher than planned
R-03 | Data loss due to system failure | Technical | 2 | 5 | 10 | Regular data backups | IT Manager | Open | 2026-01-07 | 2026-02-07 | Backup automation pending
R-04 | Staff shortage | Human Resources | 3 | 3 | 9 | Cross-train team members | HR Manager | Open | 2026-01-08 | 2026-02-08 | Peak workload expected
R-05 | Regulatory compliance changes | Legal | 1 | 5 | 5 | Monitor regulatory updates | Legal Advisor | Open | 2026-01-09 | 2026-03-01 | Industry rules under review
R-06 | Cybersecurity breach | Security | 2 | 5 | 10 | Improve security protocols | IT Manager | In Progress | 2026-01-10 | 2026-02-10 | Staff training scheduled
R-07 | Project scope creep | Project | 4 | 3 | 12 | Approve changes formally | Project Manager | Open | 2026-01-11 | 2026-01-25 | Stakeholders request changes
R-08 | Equipment breakdown | Operational | 3 | 4 | 12 | Schedule preventive maintenance | Maintenance Lead | Open | 2026-01-12 | 2026-02-12 | Equipment nearing end of life
R-09 | Poor communication between teams | Organizational | 3 | 3 | 9 | Weekly coordination meetings | Team Lead | In Progress | 2026-01-13 | 2026-01-27 | New teams involved
R-10 | Missed project deadline | Project | 2 | 4 | 8 | Adjust timeline and resources | Project Manager | Open | 2026-01-14 | 2026-02-14 | Dependent on vendor delivery
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0