## Blank Construction Schedule Tem
Construction Schedule Template Designed by Spreadsheet Daddy
Project Name |  |  | Project Start Date | Project End Date
Project Manager
Project Status
Location
[5 empty] | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4 |  |  | Phase 5 |  |  | Phase 6 |  |  | Phase 7 |  |  | Phase 8
Task | Assigned To | Progress (%) | Start Date | End Date | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24
[Category]
[Category]
[Category]
[Category]
[Category]

## Construction Schedule Template
Construction Schedule Template Designed by Spreadsheet Daddy
Project Name | Oakwood Residential Complex |  | Project Start Date | Project End Date
Project Manager | Sarah Johnson |  | 2026-03-01 | 2026-08-15
Project Status | In Progress
Location | Springfield
[5 empty] | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4 |  |  | Phase 5 |  |  | Phase 6 |  |  | Phase 7 |  |  | Phase 8
Task | Assigned To | Progress (%) | Start Date | End Date | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24
Site Preparation
Clear Land | Ground Crew | 100% | 2026-03-01 | 2026-03-07
Excavate & Level | Excavation Team | 80% | 2026-03-05 | 2026-03-14
Foundation
Pour Footings | Concrete Team | 70% | 2026-03-15 | 2026-03-21
Pour Slab | Concrete Team | 50% | 2026-03-22 | 2026-03-28
Structural Framing
Wall Framing | Framing Crew | 40% | 2026-03-29 | 2026-04-18
Roof Framing | Framing Crew | 20% | 2026-04-12 | 2026-04-25
Electrical & Plumbing
Rough Electrical | Electricians | 10% | 2026-04-26 | 2026-05-10
Plumbing Rough-In | Plumbers | 10% | 2026-04-26 | 2026-05-10
Interior and Exterior Finishing
Drywall Installation | Interior Crew | 0% | 2026-05-11 | 2026-05-25
Painting | Painters | 0% | 2026-05-26 | 2026-06-10
Roofing | Roofing Team | 0% | 2026-06-11 | 2026-06-25
Windows & Doors | Exterior Crew | 0% | 2026-06-20 | 2026-07-05
Landscaping | Landscaping Crew | 0% | 2026-07-06 | 2026-07-20
Final Inspection | Project Manager | 0% | 2026-07-21 | 2026-08-15