## Blank OKR Template
OKR Template Designed by Spreadsheet Daddy
Key Results | Priority | Owner | Start Date | End Date | Progress (%) | Status | Notes
[Objective]
[Objective]
[Objective]
[Objective]
[Objective]

## OKR Template Example
OKR Template Designed by Spreadsheet Daddy
Key Results | Priority | Owner | Start Date | End Date | Progress (%) | Status | Notes
Increase website traffic by 50% in Q1
Grow organic search traffic from 10k to 15k visitors/month | High | Alice | 2026-02-01 | 2026-04-30 | 40% | On Track | SEO campaign started
Publish 12 blog posts per month | Medium | Bob | 2026-02-01 | 2026-04-30 | 25% | At Risk | 3 posts published so far
Increase referral traffic from social media by 20% | Medium | Carol | 2026-02-01 | 2026-04-30 | 10% | At Risk | Need to boost engagement
Improve customer satisfaction
Achieve NPS score of 70+ | High | Dave | 2026-02-01 | 2026-04-30 | 50% | On Track | Survey responses collected
Reduce customer support response time to <2 hours | Medium | Eve | 2026-02-01 | 2026-04-30 | 30% | On Track | Hiring additional staff
Resolve 95% of support tickets within SLA | High | Frank | 2026-02-01 | 2026-04-30 | 20% | At Risk | Ticket backlog high
Launch new mobile app
Complete app design phase | High | Grace | 2026-02-01 | 2026-03-15 | 100% | Completed | Design approved by stakeholders
Finish app development (iOS & Android) | High | Henry | 2026-02-01 | 2026-04-15 | 60% | On Track | Backend integration ongoing
Beta test with 100 users | Medium | Irene | 2026-03-01 | 2026-04-20 | 0% | Not Started | Waiting for development completion
[Objective]
Launch 2 new product lines | High | Jack | 2026-02-01 | 2026-03-31 | 80% | On Track | Production nearly complete
Implement email marketing campaign | Medium | Karen | 2026-02-10 | 2026-04-30 | 40% | On Track | Campaign draft ready
Optimize checkout process to reduce cart abandonment by 15% | High | Liam | 2026-02-01 | 2026-04-15 | 20% | At Risk | UX testing needed
Improve team productivity
Conduct 5 team training sessions | Medium | Mia | 2026-02-01 | 2026-04-30 | 60% | On Track | 3 sessions completed
Implement project management tool for all teams | High | Noah | 2026-02-01 | 2026-03-31 | 100% | Completed | Tool fully adopted
Reduce average task completion time by 20% | High | Olivia | 2026-02-01 | 2026-04-30 | 15% | At Risk | Monitoring metrics ongoing