## Blank Progress Tracker Template
Progress Tracker Template Designed by Spreadsheet Daddy
Task | Priority | Start Date | End Date | Status | Progress (%) | Notes

## Progress Tracker Template Examp
Progress Tracker Template Designed by Spreadsheet Daddy
Task | Priority | Start Date | End Date | Status | Progress (%) | Notes
Write project proposal | High | 2026-02-01 | 2026-02-05 | Completed | 100% | Submitted to manager
Collect market research | Medium | 2026-02-02 | 2026-02-10 | In Progress | 50% | Waiting for survey responses
Design website homepage | High | 2026-02-03 | 2026-02-12 | In Progress | 30% | Wireframe approved
Create logo concepts | Medium | 2026-02-04 | 2026-02-08 | Completed | 100% | Sent to branding team
Develop backend API | High | 2026-02-05 | 2026-02-20 | In Progress | 40% | Database schema ready
Test mobile app | High | 2026-02-06 | 2026-02-18 | Not Started | 0% | QA team assigned
Prepare marketing plan | Medium | 2026-02-07 | 2026-02-15 | In Progress | 25% | Initial draft done
Set up social media accounts | Low | 2026-02-08 | 2026-02-12 | Completed | 100% | Facebook, Instagram, Twitter created
Conduct competitor analysis | Medium | 2026-02-09 | 2026-02-14 | In Progress | 60% | Analysis in Excel
Write blog post series | Medium | 2026-02-10 | 2026-02-20 | Not Started | 0% | Topics selected
Create email newsletter | Low | 2026-02-11 | 2026-02-15 | In Progress | 20% | Template ready
Organize team meeting | High | 2026-02-12 | 2026-02-12 | Completed | 100% | Meeting minutes recorded
Set up project timeline | High | 2026-02-01 | 2026-02-03 | Completed | 100% | Gantt chart created
Review client feedback | Medium | 2026-02-13 | 2026-02-17 | Not Started | 0% | Waiting for feedback
Launch beta version | High | 2026-02-18 | 2026-02-25 | Not Started | 0% | Development ongoing