## Blank Project Timeline Template
Project Timeline Template Designed by Spreadsheet Daddy
Project Name |  |  | Project Start Date | Project End Date
Project Manager
Project Status
[5 empty] | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4
Action | Responsible Person | Progress (%) | Start Date | End Date | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
[Task]
[Task]
[Task]
[Task]
[Task]

## Project Timeline Template Examp
Project Timeline Template Designed by Spreadsheet Daddy
Project Name | Website Redesign Project |  | Project Start Date | Project End Date
Project Manager | Jessica Miller |  | 2026-03-01 | 2026-05-31
Project Status | In Progress
[5 empty] | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4
Action | Responsible Person | Progress (%) | Start Date | End Date | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Design Homepage
Create wireframe | Alice Johnson | 100% | 2026-03-01 | 2026-03-07
Review wireframe | Bob Smith | 100% | 2026-03-08 | 2026-03-10
Design visual mockup | Alice Johnson | 70% | 2026-03-11 | 2026-03-21
Approval from client | Carol Lee | 0% | 2026-03-22 | 2026-03-24
Backend Development
Set up database | Daniel Kim | 50% | 2026-03-08 | 2026-03-18
Develop API endpoints | Emma Davis | 30% | 2026-03-19 | 2026-04-02
Testing API | Frank Wilson | 0% | 2026-04-03 | 2026-04-10
Content Creation
Write homepage copy | Grace Young | 100% | 2026-03-05 | 2026-03-12
Gather images | Hannah Clark | 80% | 2026-03-06 | 2026-03-20
SEO optimization | Ian Martinez | 20% | 2026-03-21 | 2026-04-05
Testing & QA
Internal testing | Jack Thompson | 0% | 2026-04-06 | 2026-04-20
Bug fixing | Kelly Rivera | 0% | 2026-04-21 | 2026-05-05
Final client approval | Laura Nguyen | 0% | 2026-05-06 | 2026-05-15
Launch website | Project Team | 0% | 2026-05-20 | 2026-05-31
[Task]