## Blank Workflow Template
Workflow Template Designed by Spreadsheet Daddy
Task | Priority | Assigned to | Start Date | End Date | Status | Progress (%) | Dependencies | Notes

## Workflow Template Example
Workflow Template Designed by Spreadsheet Daddy
Task | Priority | Assigned to | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Define project goals | High | Emma | 2026-02-01 | 2026-02-02 | Completed | 100% |  | Approved by management
Market research | High | Liam | 2026-02-02 | 2026-02-06 | Completed | 100% | Define project goals | Competitor analysis included
Create project timeline | High | Olivia | 2026-02-03 | 2026-02-05 | Completed | 100% | Define project goals | Shared with team
Develop product concept | High | Noah | 2026-02-06 | 2026-02-12 | In Progress | 70% | Market research | Initial draft ready
Design branding assets | Medium | Ava | 2026-02-08 | 2026-02-14 | In Progress | 60% | Develop product concept | Logo finalized
Build landing page | High | Ethan | 2026-02-10 | 2026-02-18 | In Progress | 50% |  | Waiting for final copy
Write website copy | High | Sophia | 2026-02-09 | 2026-02-15 | Completed | 100% | Market research | SEO optimized
Set up email campaign | Medium | Mason | 2026-02-14 | 2026-02-20 | Not Started | 0% | Write website copy | Templates prepared
Prepare social media plan | Medium | Isabella | 2026-02-12 | 2026-02-17 | In Progress | 40% |  | Content calendar drafted
Develop ad creatives | Medium | Lucas | 2026-02-13 | 2026-02-19 | Not Started | 0% | Design branding assets | Awaiting visuals
QA testing (website) | High | Mia | 2026-02-19 | 2026-02-22 | Not Started | 0% | Build landing page | Functional testing required
Launch email campaign | High | Mason | 2026-02-21 | 2026-02-21 | Not Started | 0% | Set up email campaign | Scheduled for 10 AM
Launch social media ads | High | Lucas | 2026-02-22 | 2026-02-22 | Not Started | 0% | Develop ad creatives | Budget approved
Product launch day | High | Emma | 2026-02-23 | 2026-02-23 | Not Started | 0% |  | Cross-team coordination
Post-launch analysis | Medium | Liam | 2026-02-24 | 2026-02-28 | Not Started | 0% | Product launch day | Review KPIs