## Blank Conference Planning Templ
Conference Planning Template Designed by Spreadsheet Daddy
Conference Name
Event Date
Venue
Task | Category | Owner | Due Date | Priority | Status | Notes

## Conference Planning Template Ex
Conference Planning Template Designed by Spreadsheet Daddy
Conference Name | Future Business & Technology Summit 2026
Event Date | 2026-09-15
Venue | Grand City Convention Center
Task | Category | Owner | Due Date | Priority | Status | Notes
Finalize conference theme | Planning | Emma Wilson | 2026-04-01 | High | Complete | Theme: "Innovation for Tomorrow" approved
Create event budget | Finance | Michael Brown | 2026-04-05 | High | Complete | Initial budget of $45,000 created
Book conference venue | Venue | Sarah Johnson | 2026-04-10 | High | Complete | Contract signed with venue
Confirm keynote speakers | Speakers | David Lee | 2026-05-01 | High | In Progress | Waiting for final confirmation
Design conference website | Marketing | Olivia Smith | 2026-05-15 | Medium | Complete | Registration page launched
Set up attendee registration system | Registration | James Carter | 2026-05-20 | High | In Progress | Testing payment process
Contact potential sponsors | Sponsorship | Emma Wilson | 2026-06-01 | High | In Progress | 15 companies contacted
Arrange catering services | Catering | Sarah Johnson | 2026-06-15 | Medium | Not Started | Requesting vendor quotes
Hire audio/visual team | Equipment | Michael Brown | 2026-06-20 | High | Not Started | Compare three suppliers
Create event schedule | Planning | David Lee | 2026-07-01 | Medium | Not Started | Include keynote and workshops
Prepare marketing campaign | Marketing | Olivia Smith | 2026-07-10 | High | In Progress | Social media ads planned
Order printed materials | Printing | James Carter | 2026-07-25 | Medium | Not Started | Badges, banners, brochures
Recruit event volunteers | Staffing | Emma Wilson | 2026-08-01 | Medium | Not Started | Need 20 volunteers
Arrange speaker travel | Speakers | David Lee | 2026-08-10 | Medium | Not Started | Book flights and hotels
Confirm attendee list | Registration | James Carter | 2026-08-25 | High | Not Started | Final registration check
Prepare welcome packages | Attendee Experience | Olivia Smith | 2026-09-01 | Low | Not Started | Include schedules and gifts
Conduct venue walkthrough | Venue | Sarah Johnson | 2026-09-05 | High | Not Started | Check rooms and equipment
Finalize catering numbers | Catering | Michael Brown | 2026-09-07 | High | Not Started | Confirm meal preferences
Send reminder emails | Communication | Olivia Smith | 2026-09-10 | Medium | Not Started | Send final event details
Complete event setup | Operations | Emma Wilson | 2026-09-14 | High | Not Started | Prepare venue one day before