## Blank Decommissioning Checklist
Decommissioning Checklist Template Designed by Spreadsheet Daddy
Task | Category | Owner | Due Date | Done | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Decommissioning Checklist Templ
Decommissioning Checklist Template Designed by Spreadsheet Daddy
Task | Category | Owner | Due Date | Done | Notes
Obtain decommissioning approval | Approval | Project Manager | 2026-09-01 | TRUE | Approval received from management
Notify stakeholders | Communication | Project Manager | 2026-09-02 | TRUE | All departments informed
Create decommissioning plan | Planning | Project Manager | 2026-09-03 | TRUE | Timeline approved
Back up critical data | Backup | IT Administrator | 2026-09-04 | TRUE | Backup verified successfully
Archive required records | Documentation | Records Manager | 2026-09-05 | FALSE | Awaiting final review
Remove user accounts | IT | System Administrator | 2026-09-06 | FALSE | Disable all active accounts
Revoke system permissions | Security | IT Security | 2026-09-06 | FALSE | Remove administrative access
Wipe storage devices | Data Security | IT Security | 2026-09-07 | FALSE | Secure data erasure required
Disconnect power and network cables | Facilities | Facilities Manager | 2026-09-08 | FALSE | Coordinate with IT team
Remove asset from inventory | Asset Management | Asset Coordinator | 2026-09-09 | FALSE | Update asset register
Cancel software licenses | Licensing | IT Administrator | 2026-09-10 | FALSE | Avoid renewal charges
Terminate maintenance contracts | Vendor Management | Procurement Officer | 2026-09-10 | FALSE | Confirm vendor cancellation
Remove equipment from service | Operations | Operations Manager | 2026-09-11 | FALSE | Equipment no longer in use
Dispose of or recycle equipment | Disposal | Facilities Manager | 2026-09-12 | FALSE | Follow recycling policy
Update network and system documentation | Documentation | IT Administrator | 2026-09-13 | FALSE | Remove retired asset references
Perform final compliance review | Compliance | Compliance Officer | 2026-09-14 | FALSE | Verify all requirements completed
Conduct final site inspection | Inspection | Facilities Manager | 2026-09-15 | FALSE | Ensure area is cleared
Close decommissioning project | Project Closure | Project Manager | 2026-09-16 | FALSE | Archive project documentation
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE