## Blank Go Live Checklist Templat
Go Live Checklist Template Designed by Spreadsheet Daddy
Task | Category | Owner | Due Date | Status | Notes

## Go Live Checklist Template Exam
Go Live Checklist Template Designed by Spreadsheet Daddy
Task | Category | Owner | Due Date | Status | Notes
Finalize project scope and requirements | Planning | Project Manager | 2026-08-01 | Completed | All requirements approved
Complete system development | Development | Development Team | 2026-08-10 | Completed | All features implemented
Perform functional testing | Testing | QA Team | 2026-08-15 | Completed | Test cases passed
Complete user acceptance testing (UAT) | Testing | Business Team | 2026-08-20 | Completed | Users approved system
Migrate production data | Data Migration | IT Team | 2026-08-25 | In Progress | Data validation underway
Review security settings | Security | Security Team | 2026-08-28 | In Progress | Access permissions being checked
Create user accounts | Infrastructure | IT Support | 2026-09-01 | Not Started | Waiting for final user list
Prepare training materials | Training | Training Team | 2026-09-02 | Completed | User guides created
Conduct employee training sessions | Training | HR Team | 2026-09-05 | In Progress | Sessions scheduled
Complete backup and recovery test | Technical | IT Team | 2026-09-06 | Not Started | Disaster recovery plan review
Prepare launch communication | Communication | Marketing Team | 2026-09-07 | Completed | Announcement sent
Confirm vendor readiness | Vendor Management | Project Manager | 2026-09-08 | Pending Review | Waiting for vendor confirmation
Complete final system review | Approval | Project Sponsor | 2026-09-10 | Not Started | Final approval required
Schedule go-live deployment | Deployment | IT Team | 2026-09-12 | Not Started | Deployment window reserved
Monitor system after launch | Support | Support Team | 2026-09-16 | Not Started | 24-hour monitoring planned