## Blank Issue Tracker Template
Issue Tracker Template Designed by Spreadsheet Daddy
Issue ID | Date Reported | Title | Description | Category | Priority | Assigned To | Status | Due Date | Date Resolved | Notes

## Issue Tracker Template Example
Issue Tracker Template Designed by Spreadsheet Daddy
Issue ID | Date Reported | Title | Description | Category | Priority | Assigned To | Status | Due Date | Date Resolved | Notes
ISS-001 | 2026-07-01 | Login Page Error | Users unable to sign in with valid credentials | Bug | Critical | John Smith | Resolved | 2026-07-03 | 2026-07-02 | Authentication fix deployed
ISS-002 | 2026-07-01 | Slow Dashboard Loading | Dashboard takes over 15 seconds to load | Performance | High | Emily Davis | In Progress | 2026-07-06 |  | Database optimization underway
ISS-003 | 2026-07-02 | Broken Contact Form | Form submissions not being received | Bug | High | Michael Brown | Resolved | 2026-07-04 | 2026-07-03 | Email integration restored
ISS-004 | 2026-07-02 | Update User Guide | Add new reporting feature documentation | Documentation | Medium | Sarah Wilson | Open | 2026-07-08 |  | Awaiting feature completion
ISS-005 | 2026-07-03 | Mobile Layout Issue | Navigation overlaps on small screens | User Interface | Medium | David Johnson | Testing | 2026-07-07 |  | Waiting for QA approval
ISS-006 | 2026-07-03 | SSL Certificate Renewal | Website certificate expires soon | Security | Critical | Jessica Moore | Resolved | 2026-07-05 | 2026-07-04 | Certificate renewed
ISS-007 | 2026-07-04 | API Timeout | External API requests timing out | Integration | High | Kevin Hall | In Progress | 2026-07-09 |  | Vendor contacted
ISS-008 | 2026-07-04 | Printer Offline | Office printer unavailable | Hardware | Low | Brian Scott | Closed | 2026-07-05 | 2026-07-04 | Network cable replaced
ISS-009 | 2026-07-05 | Duplicate Customer Records | Duplicate entries in CRM | Database | High | Laura Green | Resolved | 2026-07-08 | 2026-07-07 | Duplicate cleanup completed
ISS-010 | 2026-07-05 | Feature Request: Dark Mode | Add dark theme option | Enhancement | Low | Amanda Young | Blocked | 2026-08-01 |  | Planned for next release
ISS-011 | 2026-07-06 | Email Notifications Delayed | Alerts delivered several hours late | Email | Medium | Ethan Walker | Resolved | 2026-07-09 | 2026-07-08 | SMTP queue optimized
ISS-012 | 2026-07-06 | Missing Sales Report | Weekly report failed to generate | Reporting | High | Olivia Lewis | Open | 2026-07-10 |  | Investigating scheduled task
ISS-013 | 2026-07-07 | Password Reset Failure | Reset emails not sent | Security | High | Daniel White | In Progress | 2026-07-11 |  | Email service under review
ISS-014 | 2026-07-07 | Incorrect Tax Calculation | Sales tax rounding error | Finance | Critical | Rachel Baker | Testing | 2026-07-09 |  | Fix verified in staging
ISS-015 | 2026-07-08 | Inventory Sync Error | Stock quantities not updating | Inventory | High | Jason King | Resolved | 2026-07-12 | 2026-07-10 | Sync service restarted
ISS-016 | 2026-07-08 | Broken Download Link | PDF download returns 404 error | Website | Medium | Megan Adams | Closed | 2026-07-09 | 2026-07-08 | File path corrected
ISS-017 | 2026-07-09 | VPN Connection Drops | Remote users losing connection | Network | Medium | Andrew Perez | On Hold | 2026-07-15 |  | ISP investigation ongoing
ISS-018 | 2026-07-09 | Calendar Sync Failure | Meetings not syncing with Outlook | Integration | Medium | Sophia Turner | Assigned | 2026-07-13 |  | Developer reviewing logs
ISS-019 | 2026-07-10 | Missing Product Images | Images not displaying on catalog pages | Website | Low | Christopher Lee | Resolved | 2026-07-11 | 2026-07-10 | CDN cache refreshed
ISS-020 | 2026-07-10 | Backup Job Failed | Nightly database backup unsuccessful | Infrastructure | Critical | Hannah Martin | Resolved | 2026-07-11 | 2026-07-10 | Backup completed after retry