## Blank Mutual Action Plan Templa
Mutual Action Plan Template Designed by Spreadsheet Daddy
Milestone | Task | Owner | Due Date | Status | Notes

## Mutual Action Plan Template Exa
Mutual Action Plan Template Designed by Spreadsheet Daddy
Milestone | Task | Owner | Due Date | Status | Notes
Project Kickoff | Schedule kickoff meeting | Account Manager | 2026-07-07 | Completed | Meeting invitation sent
Project Kickoff | Conduct stakeholder introductions | Project Manager | 2026-07-08 | Completed | Key contacts identified
Requirements Gathering | Submit business requirements document | Client Team | 2026-07-10 | In Progress | Draft under review
Requirements Gathering | Review requirements document | Business Analyst | 2026-07-12 | Not Started | Awaiting submission
Technical Assessment | Complete technical discovery session | Solutions Engineer | 2026-07-14 | Not Started | Schedule pending
Technical Assessment | Assess system compatibility | IT Team | 2026-07-16 | Not Started | Requires API access
Proposal Phase | Prepare project proposal | Sales Team | 2026-07-18 | Not Started | Include implementation timeline
Proposal Phase | Review and approve proposal | Client Sponsor | 2026-07-21 | Not Started | Executive approval required
Contracting | Submit legal documents | Legal Team | 2026-07-23 | Not Started | NDA already signed
Contracting | Finalize contract terms | Procurement Team | 2026-07-25 | Not Started | Pricing review required
Contracting | Execute agreement | Both Parties | 2026-07-28 | Not Started | Electronic signature process
Implementation Planning | Develop implementation plan | Project Manager | 2026-07-30 | Not Started | Timeline to be confirmed
Implementation Planning | Assign project resources | Operations Team | 2026-08-01 | Not Started | Staffing approval pending
System Setup | Configure software environment | Technical Team | 2026-08-05 | Not Started | Test environment first
System Setup | Create user accounts | IT Administrator | 2026-08-07 | Not Started | User list required
Data Migration | Prepare data export files | Client Team | 2026-08-10 | Not Started | Validate source data
Data Migration | Import and validate data | Data Specialist | 2026-08-14 | Not Started | Quality checks required
Training | Conduct user training sessions | Training Manager | 2026-08-18 | Not Started | Three sessions planned
Go-Live | Launch production environment | Technical Team | 2026-08-22 | Not Started | Final approval needed
Project Closure | Complete post-launch review | Project Manager | 2026-08-29 | Not Started | Collect stakeholder feedback