## Blank Workback Schedule Templat
Workback Schedule Template Designed by Spreadsheet Daddy
Task | Owner | Start Date | Due Date | Duration | Notes

## Workback Schedule Template Exam
Workback Schedule Template Designed by Spreadsheet Daddy
Task | Owner | Start Date | Due Date | Duration | Notes
Define project goals | Sarah Johnson | 2026-01-02 | 2026-01-05 | 4 days | Establish project scope and objectives
Conduct market research | Michael Chen | 2026-01-06 | 2026-01-15 | 10 days | Analyze competitors and target audience
Create project timeline | Emma Davis | 2026-01-16 | 2026-01-18 | 3 days | Develop master schedule
Approve budget | David Wilson | 2026-01-19 | 2026-01-22 | 4 days | Finalize project budget allocation
Assemble project team | Sarah Johnson | 2026-01-23 | 2026-01-27 | 5 days | Assign roles and responsibilities
Design initial concepts | Lisa Martinez | 2026-01-28 | 2026-02-10 | 14 days | Create design mockups
Review design concepts | Project Team | 2026-02-11 | 2026-02-13 | 3 days | Gather stakeholder feedback
Revise designs | Lisa Martinez | 2026-02-14 | 2026-02-20 | 7 days | Implement requested changes
Develop prototype | James Brown | 2026-02-21 | 2026-03-10 | 18 days | Build initial prototype
Internal testing | QA Team | 2026-03-11 | 2026-03-17 | 7 days | Test functionality and performance
Fix identified issues | Development Team | 2026-03-18 | 2026-03-25 | 8 days | Resolve bugs and errors
Prepare marketing materials | Olivia Taylor | 2026-03-26 | 2026-04-05 | 11 days | Create promotional assets
Conduct user testing | Research Team | 2026-04-06 | 2026-04-12 | 7 days | Gather user feedback
Implement user feedback | Development Team | 2026-04-13 | 2026-04-22 | 10 days | Make final improvements
Final quality assurance | QA Team | 2026-04-23 | 2026-04-28 | 6 days | Complete final testing
Prepare launch documentation | Emma Davis | 2026-04-29 | 2026-05-04 | 6 days | Create user guides and manuals
Train support staff | Michael Chen | 2026-05-05 | 2026-05-08 | 4 days | Conduct training sessions
Final stakeholder approval | Executive Team | 2026-05-09 | 2026-05-12 | 4 days | Obtain final sign-off
Launch preparation | Project Team | 2026-05-13 | 2026-05-15 | 3 days | Complete launch checklist
Product launch | All Teams | 2026-05-16 | 2026-05-16 | 1 day | Official project launch