## Blank Change Order Log Template
Change Order Log Template Designed by Spreadsheet Daddy
Change Order ID | Date Requested | Description | Category | Requested By | Cost Impact | Schedule Impact | Approval Status | Approved By | Completion Status | Notes

## Change Order Log Template Examp
Change Order Log Template Designed by Spreadsheet Daddy
Change Order ID | Date Requested | Description | Category | Requested By | Cost Impact | Schedule Impact | Approval Status | Approved By | Completion Status | Notes
CO-001 | 2026-08-01 | Add additional electrical outlets in meeting rooms | Scope Change | Client Representative | 1250 | +3 Days | Approved | Project Manager | Completed | Additional outlets installed and tested
CO-002 | 2026-08-03 | Replace standard flooring with premium material | Material Change | Client | 4800 | +5 Days | Approved | Client Director | In Progress | Materials ordered
CO-003 | 2026-08-05 | Modify office layout design | Design Change | Architect | 2500 | +4 Days | Under Review | Pending | Not Started | Awaiting design approval
CO-004 | 2026-08-06 | Upgrade HVAC system capacity | Quality Improvement | Engineering Team | 8500 | +7 Days | Approved | Project Director | In Progress | Installation scheduled
CO-005 | 2026-08-08 | Add additional security cameras | Client Request | Building Owner | 3200 | +2 Days | Approved | Client Manager | Completed | Cameras installed successfully
CO-006 | 2026-08-10 | Extend construction timeline due to weather delays | Schedule Extension | Contractor | 0 | +10 Days | Approved | Project Manager | Completed | Updated project schedule issued
CO-007 | 2026-08-12 | Change paint color selection | Material Change | Interior Designer | 650 | +1 Day | Approved | Client Representative | Completed | New paint applied
CO-008 | 2026-08-14 | Add additional storage cabinets | Additional Work | Client | 2100 | +3 Days | Pending Approval | Pending | Not Started | Cost estimate submitted
CO-009 | 2026-08-15 | Correct plumbing design issue | Error Correction | Site Supervisor | 1900 | +2 Days | Approved | Engineering Manager | Completed | Issue resolved
CO-010 | 2026-08-17 | Upgrade lighting fixtures throughout building | Quality Improvement | Electrical Contractor | 5600 | +4 Days | Approved | Project Director | In Progress | Installation underway
CO-011 | 2026-08-18 | Add additional data network points | Scope Change | IT Team | 3750 | +3 Days | Under Review | Pending | Not Started | Technical review required
CO-012 | 2026-08-20 | Replace damaged construction materials | Material Change | Contractor | 1400 | +1 Day | Approved | Site Manager | Completed | Replacement materials installed
CO-013 | 2026-08-22 | Update fire safety system requirements | Regulatory Requirement | Safety Inspector | 6200 | +6 Days | Approved | Compliance Officer | In Progress | Waiting for inspection
CO-014 | 2026-08-24 | Add additional landscaping features | Client Request | Property Owner | 7800 | +8 Days | Pending Approval | Pending | Not Started | Proposal submitted
CO-015 | 2026-08-26 | Change door hardware specifications | Material Change | Architect | 950 | +1 Day | Approved | Project Manager | Completed | Hardware replaced
CO-016 | 2026-08-28 | Revise project documentation | Design Change | Project Engineer | 500 | No Impact | Approved | Project Director | Completed | Documents updated
CO-017 | 2026-08-30 | Add additional inspection requirements | Regulatory Requirement | Safety Team | 1100 | +2 Days | Approved | Safety Manager | In Progress | Inspections scheduled
CO-018 | 2026-09-01 | Install upgraded access control system | Security Upgrade | Client | 9500 | +7 Days | Rejected | N/A | Cancelled | Cost exceeded approved budget