## Blank Construction Punch List T
Construction Punch List Template Designed by Spreadsheet Daddy
Item ID | Area/Location | Description | Category | Assigned To | Priority | Due Date | Status | Completion Date | Notes

## Construction Punch List Templat
Construction Punch List Template Designed by Spreadsheet Daddy
Item ID | Area/Location | Description | Category | Assigned To | Priority | Due Date | Status | Completion Date | Notes
PL-001 | Main Lobby | Touch up wall paint near entrance | Painting | Apex Finishes | Medium | 2026-08-12 | Completed | 2026-08-10 | Paint color matched approved sample
PL-002 | Conference Room A | Install missing ceiling light fixture | Electrical | BrightLine Electric | High | 2026-08-11 | In Progress | N/A | Fixture has been ordered
PL-003 | Restroom 2 | Repair leaking faucet | Plumbing | ClearFlow Plumbing | High | 2026-08-09 | Completed | 2026-08-08 | Leak resolved and fixture tested
PL-004 | Office 104 | Replace damaged floor tile | Flooring | Metro Flooring | Medium | 2026-08-14 | Open | N/A | Replacement tile available onsite
PL-005 | Main Entrance | Adjust door closer | Doors and Windows | SecureDoor Services | Low | 2026-08-15 | Completed | 2026-08-13 | Door now closes properly
PL-006 | Break Room | Install cabinet handles | Finishing | BuildRight Interiors | Low | 2026-08-16 | Open | N/A | Hardware delivered
PL-007 | Server Room | Seal cable opening in wall | Finishing | Site Maintenance | Medium | 2026-08-13 | Completed | 2026-08-12 | Opening sealed and finished
PL-008 | Mechanical Room | Label HVAC equipment | HVAC | ClimateTech Services | Medium | 2026-08-18 | In Progress | N/A | Labels being prepared
PL-009 | Stairwell | Repair damaged handrail section | Safety | General Contractor | High | 2026-08-10 | Completed | 2026-08-09 | Handrail secured and inspected
PL-010 | Office 201 | Replace cracked window pane | Doors and Windows | GlassWorks Inc. | High | 2026-08-20 | Open | N/A | Glass replacement scheduled
PL-011 | Kitchen | Adjust cabinet door alignment | Finishing | Apex Finishes | Low | 2026-08-17 | Completed | 2026-08-15 | Doors aligned correctly
PL-012 | Parking Area | Repaint faded parking lines | Exterior | Site Maintenance | Medium | 2026-08-22 | Open | N/A | Weather dependent
PL-013 | Reception Area | Install missing outlet cover | Electrical | BrightLine Electric | High | 2026-08-11 | Completed | 2026-08-10 | Cover installed and secured
PL-014 | Restroom 1 | Replace damaged ceiling tile | Finishing | BuildRight Interiors | Medium | 2026-08-19 | In Progress | N/A | Replacement material delivered
PL-015 | Office 106 | Correct HVAC temperature issue | HVAC | ClimateTech Services | High | 2026-08-16 | Completed | 2026-08-15 | Thermostat recalibrated
PL-016 | Loading Area | Repair damaged concrete edge | Structural | General Contractor | Medium | 2026-08-24 | Open | N/A | Repair included in next site visit
PL-017 | Hallway B | Touch up scuffed wall sections | Painting | Apex Finishes | Low | 2026-08-21 | Completed | 2026-08-19 | Touch-ups completed
PL-018 | Electrical Room | Add missing equipment labels | Electrical | BrightLine Electric | Medium | 2026-08-23 | In Progress | N/A | Labels awaiting final verification
PL-019 | Exterior Entrance | Clean construction debris | Cleaning | Final Clean Team | Medium | 2026-08-25 | Open | N/A | Final cleaning scheduled
PL-020 | Main Office | Complete final door hardware inspection | Doors and Windows | SecureDoor Services | High | 2026-08-26 | Ready for Inspection | N/A | Awaiting project manager inspection