## Blank Product Backlog Template
Product Backlog Template Designed by Spreadsheet Daddy
Item ID | User Story | Type | Priority | Description | Assigned To | Story Points | Status | Sprint | Due Date | Notes

## Product Backlog Template Exampl
Product Backlog Template Designed by Spreadsheet Daddy
Item ID | User Story | Type | Priority | Description | Assigned To | Story Points | Status | Sprint | Due Date | Notes
PB-001 | As a user, I want to create an account so I can access the platform | Feature | Critical | Add registration with email and password | Emma Carter | 5 | In Progress | Sprint 1 | 2026-08-07 | Registration flow under development
PB-002 | As a user, I want to log in securely so I can access my account | Feature | Critical | Implement login and authentication | James Wilson | 5 | In Progress | Sprint 1 | 2026-08-08 | Authentication testing underway
PB-003 | As a user, I want to reset my password if I forget it | Feature | High | Add password recovery process | Sarah Miller | 3 | Ready | Sprint 1 | 2026-08-09 | Email reset link required
PB-004 | As a user, I want to edit my profile information | Feature | Medium | Allow users to update profile details | Michael Brown | 3 | Backlog | Sprint 2 | 2026-08-15 | Profile fields to be confirmed
PB-005 | As a user, I want to search for products quickly | Feature | High | Add keyword search functionality | Olivia Davis | 8 | In Progress | Sprint 2 | 2026-08-16 | Search design approved
PB-006 | As a user, I want to filter search results | Feature | Medium | Add category and price filters | Daniel Taylor | 5 | Backlog | Sprint 2 | 2026-08-18 | Depends on search functionality
PB-007 | As a customer, I want to add products to my cart | Feature | Critical | Create shopping cart functionality | Emily Clark | 8 | Ready | Sprint 2 | 2026-08-19 | Cart should retain selected items
PB-008 | As a customer, I want to remove products from my cart | Feature | High | Add remove item functionality | Robert Lewis | 3 | Backlog | Sprint 3 | 2026-08-22 | Include quantity updates
PB-009 | As a customer, I want to complete checkout securely | Feature | Critical | Create checkout and order confirmation flow | Amanda White | 13 | Backlog | Sprint 3 | 2026-08-26 | Payment integration required
PB-010 | As a customer, I want to receive an order confirmation | Feature | High | Send confirmation after successful order | David Harris | 5 | Backlog | Sprint 3 | 2026-08-27 | Email template needed
PB-011 | As a user, I want the website to load quickly | Improvement | High | Optimize page loading and image sizes | Sophia Martin | 5 | In Review | Sprint 1 | 2026-08-10 | Performance improvements completed
PB-012 | As a user, I want the site to work well on mobile devices | Improvement | High | Improve responsive layouts | William Clark | 8 | In Progress | Sprint 2 | 2026-08-20 | Mobile testing ongoing
PB-013 | As an administrator, I want to view customer accounts | Feature | Medium | Create customer management dashboard | Mia Wilson | 8 | Ready | Sprint 3 | 2026-08-25 | Access restricted to administrators
PB-014 | As an administrator, I want to deactivate customer accounts | Feature | Medium | Add account deactivation controls | Ethan Davis | 5 | Backlog | Sprint 3 | 2026-08-28 | Confirmation required before deactivation
PB-015 | As a user, I want clear error messages | Improvement | Medium | Improve validation and error messaging | Charlotte Brown | 3 | Completed | Sprint 1 | 2026-08-06 | Messages reviewed by product team
PB-016 | As a customer, I want to see my order history | Feature | Medium | Display previous purchases and order details | Noah Taylor | 8 | Backlog | Sprint 4 | 2026-09-03 | Requires order database
PB-017 | As a customer, I want to track my order status | Feature | High | Display current fulfillment and shipping status | Ava Martin | 8 | Backlog | Sprint 4 | 2026-09-05 | Shipping integration required
PB-018 | As a user, I want to receive notifications about important updates | Feature | Low | Add optional email notifications | Benjamin Wilson | 5 | Deferred | Sprint 4 | 2026-09-08 | Lower priority for initial release
PB-019 | As a user, I want to sign out securely | Feature | High | Add logout functionality and session cleanup | Amelia Davis | 3 | Completed | Sprint 1 | 2026-08-05 | Security review completed
PB-020 | As a product manager, I want analytics on user activity | Feature | Low | Add basic dashboard for user engagement metrics | Henry Clark | 8 | Backlog | Sprint 5 | 2026-09-12 | Metrics to be finalized