## Blank Software Deployment Check
Software Deployment Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Status | Priority | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Software Deployment Checklist T
Software Deployment Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Status | Priority | Completed | Notes
Review deployment plan | Planning | Alex Morgan | 2026-08-10 | Completed | High | TRUE | Deployment steps approved by team
Confirm release version | Planning | Emily Carter | 2026-08-10 | Completed | High | TRUE | Version 3.5.0 confirmed
Backup production database | Backup | Daniel Lee | 2026-08-11 | Completed | Critical | TRUE | Backup verified successfully
Verify server capacity | Pre-Deployment | Michael Brown | 2026-08-11 | Completed | High | TRUE | Resources meet requirements
Update environment configuration | Configuration | Sarah Wilson | 2026-08-12 | In Progress | High | FALSE | Waiting for final configuration values
Install required dependencies | Configuration | James Taylor | 2026-08-12 | Completed | Medium | TRUE | All dependencies installed
Run database migration scripts | Database | Olivia Martinez | 2026-08-13 | Not Started | Critical | FALSE | Scheduled during maintenance window
Deploy application package | Deployment | Robert Davis | 2026-08-13 | Not Started | Critical | FALSE | Waiting for approval
Perform smoke testing | Testing | Sophia Clark | 2026-08-14 | Not Started | High | FALSE | Test environment prepared
Execute functional testing | Testing | Benjamin Harris | 2026-08-14 | In Progress | High | FALSE | Testing main user workflows
Verify integrations | Validation | Mia Anderson | 2026-08-15 | In Progress | Medium | FALSE | API connections need verification
Monitor system performance | Monitoring | William Johnson | 2026-08-15 | In Progress | High | FALSE | Check logs after deployment
Notify stakeholders | Communication | Ava Thompson | 2026-08-13 | Completed | Medium | TRUE | Release announcement sent
Update technical documentation | Documentation | Ethan Wilson | 2026-08-16 | In Progress | Medium | FALSE | Updating deployment guide
Prepare rollback procedure | Rollback | Grace Miller | 2026-08-12 | Completed | Critical | TRUE | Rollback steps tested
Conduct post-deployment review | Review | Noah Anderson | 2026-08-17 | Not Started | Low | FALSE | Schedule team review meeting
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE