## Blank Sprint Backlog Template
Sprint Backlog Template Designed by Spreadsheet Daddy
Task ID | User Story | Task | Assigned To | Priority | Story Points | Status | Start Date | Due Date | Notes

## Sprint Backlog Template Example
Sprint Backlog Template Designed by Spreadsheet Daddy
Task ID | User Story | Task | Assigned To | Priority | Story Points | Status | Start Date | Due Date | Notes
SB-001 | User login | Create login page | Emma Carter | High | 3 | Done | 2026-08-03 | 2026-08-04 | Page approved
SB-002 | User login | Implement authentication | James Wilson | Critical | 5 | In Progress | 2026-08-04 | 2026-08-07 | Backend integration underway
SB-003 | Password reset | Build password reset form | Sarah Miller | High | 3 | Done | 2026-08-03 | 2026-08-05 | Form completed
SB-004 | Password reset | Configure reset email | Michael Brown | High | 3 | In Progress | 2026-08-05 | 2026-08-08 | Email template being tested
SB-005 | User profile | Create profile page | Olivia Davis | Medium | 5 | To Do | 2026-08-06 | 2026-08-11 | Design approved
SB-006 | User profile | Add profile editing | Daniel Taylor | Medium | 5 | To Do | 2026-08-07 | 2026-08-12 | Waiting for profile page
SB-007 | Product search | Build search interface | Emily Clark | High | 5 | In Progress | 2026-08-04 | 2026-08-09 | UI development underway
SB-008 | Product search | Implement search logic | Robert Lewis | High | 8 | To Do | 2026-08-07 | 2026-08-13 | Requires search API
SB-009 | Product filtering | Add category filters | Amanda White | Medium | 5 | To Do | 2026-08-10 | 2026-08-14 | Filter options defined
SB-010 | Shopping cart | Create cart component | David Harris | Critical | 8 | In Progress | 2026-08-05 | 2026-08-12 | Core functionality underway
SB-011 | Shopping cart | Add quantity controls | Sophia Martin | High | 3 | To Do | 2026-08-09 | 2026-08-13 | Depends on cart component
SB-012 | Checkout | Create checkout page | William Clark | Critical | 8 | To Do | 2026-08-10 | 2026-08-15 | Payment fields required
SB-013 | Checkout | Add order confirmation | Mia Wilson | High | 3 | To Do | 2026-08-11 | 2026-08-15 | Confirmation email also needed
SB-014 | Notifications | Configure email notifications | Ethan Davis | Medium | 5 | In Review | 2026-08-04 | 2026-08-08 | Testing notification triggers
SB-015 | Mobile experience | Adjust responsive layout | Charlotte Brown | High | 5 | In Progress | 2026-08-05 | 2026-08-12 | Testing on multiple screen sizes
SB-016 | Reporting | Create sales report | Noah Taylor | Medium | 8 | Blocked | 2026-08-06 | 2026-08-14 | Waiting for reporting requirements
SB-017 | Administration | Create user management page | Ava Martin | Medium | 8 | To Do | 2026-08-10 | 2026-08-15 | Admin access required
SB-018 | Security | Review user permissions | Benjamin Wilson | High | 5 | In Progress | 2026-08-05 | 2026-08-11 | Security review underway
SB-019 | Performance | Optimize page loading | Amelia Davis | Medium | 5 | In Review | 2026-08-03 | 2026-08-09 | Performance improvements submitted
SB-020 | Testing | Complete regression testing | Henry Clark | High | 8 | To Do | 2026-08-12 | 2026-08-15 | Begins after feature testing