## Blank Submittal Log Template
Submittal Log Template Designed by Spreadsheet Daddy
Submittal ID | Date Submitted | Description | Category | Submitted By | Reviewer | Due Date | Status | Approval Date | Revision | Notes

## Submittal Log Template Example
Submittal Log Template Designed by Spreadsheet Daddy
Submittal ID | Date Submitted | Description | Category | Submitted By | Reviewer | Due Date | Status | Approval Date | Revision | Notes
SUB-001 | 2026-08-01 | HVAC equipment specifications | Equipment Information | Mechanical Contractor | Project Engineer | 2026-08-10 | Approved | 2026-08-08 | Rev 0 | Equipment specifications accepted
SUB-002 | 2026-08-02 | Floor tile material samples | Material Samples | Interior Designer | Architect | 2026-08-12 | Approved with Comments | 2026-08-11 | Rev 1 | Selected color requires minor adjustment
SUB-003 | 2026-08-03 | Electrical layout drawings | Shop Drawings | Electrical Contractor | Design Manager | 2026-08-15 | Under Review | N/A | Rev 0 | Awaiting engineering review
SUB-004 | 2026-08-04 | Fire alarm system documentation | Technical Documents | Safety Contractor | Safety Engineer | 2026-08-14 | Approved | 2026-08-13 | Rev 0 | Meets project requirements
SUB-005 | 2026-08-05 | Concrete mix specifications | Product Data | Concrete Supplier | Site Manager | 2026-08-16 | Approved | 2026-08-15 | Rev 0 | Approved for construction use
SUB-006 | 2026-08-06 | Window installation details | Shop Drawings | Window Contractor | Architect | 2026-08-18 | Pending Approval | N/A | Rev 0 | Submitted for review
SUB-007 | 2026-08-07 | Plumbing fixture selections | Product Data | Plumbing Contractor | Project Manager | 2026-08-20 | Approved with Comments | 2026-08-19 | Rev 1 | Updated finishes requested
SUB-008 | 2026-08-08 | Safety plan documentation | Safety Documents | General Contractor | Safety Manager | 2026-08-17 | Approved | 2026-08-16 | Rev 0 | Safety procedures accepted
SUB-009 | 2026-08-09 | Elevator equipment details | Equipment Information | Elevator Supplier | Engineer | 2026-08-22 | Under Review | N/A | Rev 0 | Technical review in progress
SUB-010 | 2026-08-10 | Paint color samples | Material Samples | Painting Contractor | Interior Designer | 2026-08-21 | Approved | 2026-08-20 | Rev 0 | Final colors selected
SUB-011 | 2026-08-12 | Roofing material specifications | Product Data | Roofing Contractor | Architect | 2026-08-25 | Approved | 2026-08-24 | Rev 0 | Materials approved
SUB-012 | 2026-08-13 | Security system drawings | Shop Drawings | Security Vendor | IT Manager | 2026-08-27 | Resubmittal Required | N/A | Rev 1 | Additional details needed
SUB-013 | 2026-08-14 | Generator installation manual | Technical Documents | Electrical Supplier | Engineer | 2026-08-28 | Under Review | N/A | Rev 0 | Waiting for technical comments
SUB-014 | 2026-08-15 | Door hardware schedule | Product Data | Door Supplier | Architect | 2026-08-30 | Approved with Comments | 2026-08-29 | Rev 1 | Minor specification updates required
SUB-015 | 2026-08-16 | Waterproofing test reports | Test Reports | Waterproofing Contractor | Quality Manager | 2026-09-01 | Approved | 2026-08-31 | Rev 0 | Test results accepted
SUB-016 | 2026-08-18 | Lighting fixture catalog | Product Data | Lighting Supplier | Electrical Engineer | 2026-09-03 | Pending Approval | N/A | Rev 0 | Awaiting design approval
SUB-017 | 2026-08-20 | Structural steel drawings | Shop Drawings | Steel Contractor | Structural Engineer | 2026-09-05 | Approved | 2026-09-04 | Rev 2 | Revised drawings accepted
SUB-018 | 2026-08-22 | Installation instructions for equipment | Installation Instructions | Equipment Supplier | Project Engineer | 2026-09-07 | Under Review | N/A | Rev 0 | Review scheduled