## Blank Construction Bid Tracking
Construction Bid Tracking Template Designed by Spreadsheet Daddy
Bid ID | Project Name | Client | Location | Bid Due Date | Estimated Cost | Bid Amount | Bid Status | Submission Date | Outcome | Contact Person | Notes

## Construction Bid Tracking Templ
Construction Bid Tracking Template Designed by Spreadsheet Daddy
Bid ID | Project Name | Client | Location | Bid Due Date | Estimated Cost | Bid Amount | Bid Status | Submission Date | Outcome | Contact Person | Notes
BID-001 | Riverside Office Renovation | Riverside Properties | Chicago, IL | 2026-08-15 | 425000 | 448000 | Submitted | 2026-08-13 | Under Review | Laura Mitchell | Awaiting client decision
BID-002 | Oak Street Warehouse | Oak Industrial Group | Dallas, TX | 2026-08-22 | 780000 | 815000 | Submitted | 2026-08-20 | Awarded | James Carter | Contract negotiations underway
BID-003 | Green Valley Apartments | Green Valley Development | Denver, CO | 2026-09-01 | 1250000 | 1310000 | Estimating | N/A | Pending | Robert Wilson | Final material pricing needed
BID-004 | Downtown Retail Center | Metro Retail Partners | Austin, TX | 2026-09-05 | 620000 | 655000 | Preparing Bid | N/A | Pending | Emily Harris | Subcontractor quotes being collected
BID-005 | Westside Medical Clinic | Westside Health Group | Phoenix, AZ | 2026-09-10 | 950000 | 985000 | Submitted | 2026-09-08 | Under Review | Michael Brown | Follow-up scheduled
BID-006 | Harbor View Hotel Renovation | Harbor Hospitality | Tampa, FL | 2026-09-14 | 1480000 | 1525000 | Reviewing | N/A | Pending | Sarah Davis | Reviewing project specifications
BID-007 | Maple Elementary School | County School District | Portland, OR | 2026-09-18 | 890000 | 925000 | Not Awarded | 2026-09-15 | Not Awarded | Daniel Thompson | Another contractor selected
BID-008 | Northside Distribution Center | Northside Logistics | Columbus, OH | 2026-09-22 | 2100000 | 2185000 | Estimating | N/A | Pending | Jennifer Clark | Site visit completed
BID-009 | Lakeside Community Center | City Development Authority | Minneapolis, MN | 2026-09-25 | 540000 | 565000 | Submitted | 2026-09-23 | Under Review | Kevin Lewis | Client requested additional documentation
BID-010 | Pinecrest Apartments | Pinecrest Housing | Charlotte, NC | 2026-09-28 | 1075000 | 1120000 | Preparing Bid | N/A | Pending | Amanda Walker | Estimator reviewing drawings
BID-011 | Airport Office Expansion | Regional Airport Authority | Atlanta, GA | 2026-10-02 | 1650000 | 1720000 | Reviewing | N/A | Pending | Brian Hall | Pre-bid meeting completed
BID-012 | Main Street Restaurant Buildout | Main Street Hospitality | Nashville, TN | 2026-10-05 | 385000 | 402000 | Awarded | 2026-10-02 | Awarded | Rachel Young | Project kickoff scheduled
BID-013 | Technology Campus Phase 1 | TechPark Development | Raleigh, NC | 2026-10-10 | 3200000 | 3350000 | Submitted | 2026-10-08 | Under Review | Thomas King | Large-scale commercial project
BID-014 | Central Library Renovation | City Library Board | Boston, MA | 2026-10-14 | 725000 | 760000 | Preparing Bid | N/A | Pending | Michelle Wright | Historic building requirements
BID-015 | Industrial Plant Upgrade | Summit Manufacturing | Detroit, MI | 2026-10-18 | 1950000 | 2020000 | Estimating | N/A | Pending | Steven Scott | Equipment installation costs under review
BID-016 | Parkside Senior Living Facility | Parkside Care Group | Nashville, TN | 2026-10-22 | 1350000 | 1410000 | Submitted | 2026-10-20 | Under Review | Nicole Adams | Awaiting final evaluation
BID-017 | Eastside Fire Station | County Emergency Services | Sacramento, CA | 2026-10-25 | 680000 | 705000 | Reviewing | N/A | Pending | Christopher Green | Reviewing construction requirements
BID-018 | Sunset Shopping Plaza | Sunset Commercial Group | Las Vegas, NV | 2026-10-28 | 1100000 | 1165000 | Not Awarded | 2026-10-25 | Not Awarded | Megan Baker | Bid exceeded client's budget
BID-019 | Riverfront Parking Garage | Riverfront Development | Pittsburgh, PA | 2026-11-01 | 2450000 | 2560000 | Preparing Bid | N/A | Pending | Andrew Nelson | Structural estimate in progress
BID-020 | Cedar Grove Community Housing | Cedar Grove Housing Authority | Kansas City, MO | 2026-11-05 | 1800000 | 1875000 | New | N/A | Pending | Jessica Turner | Bid opportunity recently received