## Blank Decision Log Template
Decision Log Template Designed by Spreadsheet Daddy
Decision ID | Date | Decision | Category | Decision Maker | Reason | Impact | Status | Action Owner | Notes

## Decision Log Template Example
Decision Log Template Designed by Spreadsheet Daddy
Decision ID | Date | Decision | Category | Decision Maker | Reason | Impact | Status | Action Owner | Notes
DEC-001 | 2026-08-01 | Move project kickoff to August 10 | Project | Olivia Carter | Additional preparation time needed | Project timeline adjusted | Approved | James Wilson | Team notified of new date
DEC-002 | 2026-08-02 | Select new project management software | Technology | Michael Brown | Current system lacks required features | Improved task tracking | Approved | Sarah Davis | Implementation planned for September
DEC-003 | 2026-08-03 | Increase marketing budget for launch | Budget | Emma Taylor | Additional promotion required | Higher campaign spend | Approved | Daniel Miller | Budget updated
DEC-004 | 2026-08-04 | Use existing supplier for office equipment | Vendor | Robert Anderson | Supplier met quality and pricing requirements | No supplier transition required | Approved | Lisa Wilson | Purchase order to be issued
DEC-005 | 2026-08-05 | Add weekly project status meetings | Operations | James Clark | Improve communication between teams | Better visibility into project progress | Implemented | Emily Harris | Meetings begin next Monday
DEC-006 | 2026-08-06 | Delay website redesign to Q4 | Project | Sophia Martin | Development resources are limited | Launch timeline extended | Approved | Daniel White | Existing site will remain active
DEC-007 | 2026-08-07 | Introduce remote onboarding sessions | Staffing | William Lewis | New hires are working across multiple locations | More flexible onboarding | Approved | Amanda Brown | First session scheduled for August 20
DEC-008 | 2026-08-08 | Replace outdated office laptops | Technology | Charlotte Davis | Several devices are reaching end of life | Improved employee productivity | Approved | Michael Taylor | Replacement plan being prepared
DEC-009 | 2026-08-09 | Add customer feedback survey after support cases | Customer Service | Ethan Wilson | Need more consistent customer feedback | Better service insights | Approved | Mia Anderson | Survey draft completed
DEC-010 | 2026-08-10 | Reduce weekly team meeting length to 30 minutes | Operations | Noah Martin | Meetings regularly exceed the planned time | More time available for project work | Implemented | Ava Thompson | New format starts this week
DEC-011 | 2026-08-11 | Create standardized project reporting format | Project | Benjamin Clark | Reports currently use different formats | Easier management review | Approved | Harper Lewis | Template under development
DEC-012 | 2026-08-12 | Add backup supplier for critical materials | Vendor | Amelia Walker | Reduce risk of supply interruptions | Improved supply continuity | Approved | Henry Hall | Supplier evaluation underway
DEC-013 | 2026-08-13 | Launch employee training program | Training | Evelyn Young | Identified skills gaps across teams | Improved employee capabilities | Approved | Alexander King | Training topics being finalized
DEC-014 | 2026-08-14 | Consolidate duplicate reporting processes | Operations | James Wilson | Multiple teams create similar reports | Reduced administrative work | Implemented | Sarah Miller | New reporting process documented
DEC-015 | 2026-08-15 | Increase project testing period by one week | Quality | Daniel Brown | Additional testing is required | Launch date may shift slightly | Approved | Olivia Harris | Testing schedule updated
DEC-016 | 2026-08-16 | Adopt quarterly vendor performance reviews | Vendor | Michael Davis | Improve supplier accountability | Better vendor performance tracking | Approved | Emma Clark | First review scheduled for October
DEC-017 | 2026-08-17 | Create centralized document storage | Technology | Rachel Taylor | Project files are stored across multiple locations | Easier document access | Under Review | Robert Lewis | Folder structure being organized
DEC-018 | 2026-08-18 | Add monthly budget review meetings | Budget | Jessica Martin | Improve visibility into spending | Better budget control | Approved | William Anderson | First review scheduled for September
DEC-019 | 2026-08-19 | Standardize client onboarding process | Customer Service | Thomas White | Onboarding steps vary between teams | More consistent client experience | Under Review | Sophia Clark | Process documentation underway
DEC-020 | 2026-08-20 | Conduct post-project review after completion | Project | Daniel Harris | Capture lessons for future projects | Improved future planning | Approved | Charlotte Wilson | Review scheduled after project close