## Blank Make-Ready Checklist Temp
Make-Ready Checklist Template Designed by Spreadsheet Daddy
Task | Area | Assigned To | Due Date | Priority | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Make-Ready Checklist Template E
Make-Ready Checklist Template Designed by Spreadsheet Daddy
Task | Area | Assigned To | Due Date | Priority | Completed | Notes
Inspect walls for damage | Living Room | James Carter | 2026-08-18 | High | TRUE | Minor scuffs found
Touch up wall paint | Living Room | Sarah Miller | 2026-08-19 | Medium | FALSE | Paint scheduled
Inspect flooring | Living Room | Michael Brown | 2026-08-18 | High | TRUE | Flooring in good condition
Check doors and locks | Entryway | Olivia Davis | 2026-08-18 | High | TRUE | Locks working properly
Test light fixtures | Entryway | Daniel Taylor | 2026-08-18 | Medium | TRUE | All lights operational
Test electrical outlets | Living Room | Emily Clark | 2026-08-19 | High | FALSE | Final inspection pending
Inspect kitchen cabinets | Kitchen | Robert Lewis | 2026-08-19 | Medium | TRUE | Cabinets cleaned and intact
Clean kitchen appliances | Kitchen | Amanda White | 2026-08-20 | High | FALSE | Deep cleaning scheduled
Check sink and faucet | Kitchen | David Harris | 2026-08-19 | High | TRUE | No leaks detected
Inspect bathroom fixtures | Bathroom | Sophia Martin | 2026-08-20 | High | TRUE | Fixtures functioning normally
Clean bathroom surfaces | Bathroom | William Clark | 2026-08-20 | High | FALSE | Cleaning in progress
Check toilet operation | Bathroom | Mia Wilson | 2026-08-20 | High | TRUE | Flush tested successfully
Inspect windows and screens | Bedrooms | Ethan Davis | 2026-08-21 | Medium | TRUE | Screens intact
Replace damaged blinds | Bedroom 1 | Charlotte Brown | 2026-08-21 | Medium | FALSE | Replacement ordered
Test smoke alarms | Hallway | Noah Taylor | 2026-08-21 | Critical | TRUE | Alarms tested successfully
Check HVAC operation | Utility Area | Ava Martin | 2026-08-22 | High | FALSE | Maintenance inspection scheduled
Replace air filter | Utility Area | Benjamin Wilson | 2026-08-22 | Medium | FALSE | New filter ready
Clean floors throughout unit | Entire Unit | Amelia Davis | 2026-08-23 | High | FALSE | Final cleaning scheduled
Remove remaining debris | Entire Unit | Henry Clark | 2026-08-23 | Medium | TRUE | Unit cleared
Complete final walkthrough | Entire Unit | Laura Brown | 2026-08-24 | Critical | FALSE | Pending completion of open tasks
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE