## Blank Multiple Project Tracking
Multiple Project Tracking Template Designed by Spreadsheet Daddy
[5 empty] | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4
Task | Responsible Person | Progress (%) | Start Date | End Date | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
[Project]
[Project]
[Project]
[Project]
[Project]

## Multiple Project Tracking Templ
Multiple Project Tracking Template Designed by Spreadsheet Daddy
[5 empty] | Phase 1 |  |  | Phase 2 |  |  | Phase 3 |  |  | Phase 4
Task | Responsible Person | Progress (%) | Start Date | End Date | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Website Redesign
Gather requirements | Emma Carter | 100% | 2026-08-03 | 2026-08-05
Create wireframes | Liam Brooks | 100% | 2026-08-06 | 2026-08-12
Design homepage | Olivia Davis | 90% | 2026-08-10 | 2026-08-21
Develop navigation | Noah Wilson | 75% | 2026-08-17 | 2026-08-28
Build product pages | James Taylor | 60% | 2026-08-24 | 2026-09-04
Configure forms | Ava Martin | 40% | 2026-08-31 | 2026-09-11
Mobile optimization | Daniel Clark | 25% | 2026-09-07 | 2026-09-18
User testing | Sophia Lewis | 10% | 2026-09-14 | 2026-09-25
Fix defects | Michael Brown | 0% | 2026-09-21 | 2026-10-02
Launch website | Sarah Wilson | 0% | 2026-10-05 | 2026-10-09
CRM Implementation
Define CRM requirements | James Carter | 100% | 2026-08-03 | 2026-08-07
Select CRM platform | Emily Davis | 100% | 2026-08-10 | 2026-08-14
Configure system | Robert Miller | 80% | 2026-08-17 | 2026-08-28
Import customer data | Mia Anderson | 60% | 2026-08-24 | 2026-09-04
Set up sales pipeline | Daniel Hall | 50% | 2026-08-31 | 2026-09-11
Configure reports | Charlotte White | 30% | 2026-09-07 | 2026-09-18
User permissions | Henry Clark | 20% | 2026-09-14 | 2026-09-25
Employee training | Amelia Lewis | 10% | 2026-09-21 | 2026-10-02
System testing | William Harris | 0% | 2026-09-28 | 2026-10-09
CRM launch | Sarah Taylor | 0% | 2026-10-12 | 2026-10-16
Office Relocation
Select new location | Emma Wilson | 100% | 2026-08-03 | 2026-08-07
Finalize lease | Michael Davis | 100% | 2026-08-10 | 2026-08-14
Plan office layout | Olivia Brown | 85% | 2026-08-17 | 2026-08-28
Order furniture | Noah Taylor | 70% | 2026-08-24 | 2026-09-04
Arrange IT equipment | Liam Clark | 55% | 2026-08-31 | 2026-09-11
Pack existing office | Ava Wilson | 40% | 2026-09-07 | 2026-09-18
Move equipment | Daniel Brown | 20% | 2026-09-14 | 2026-09-25
Set up new office | Sophia Carter | 10% | 2026-09-21 | 2026-10-02
Inspect new workspace | James Miller | 0% | 2026-09-28 | 2026-10-09
Employee move-in | Sarah Davis | 0% | 2026-10-12 | 2026-10-16
Employee Training Program
Identify training needs | Robert Carter | 100% | 2026-08-03 | 2026-08-07
Create training plan | Emily Wilson | 100% | 2026-08-10 | 2026-08-14
Develop training materials | Daniel Miller | 80% | 2026-08-17 | 2026-08-28
Prepare online modules | Mia Carter | 65% | 2026-08-24 | 2026-09-04
Schedule instructors | Henry Davis | 50% | 2026-08-31 | 2026-09-11
Conduct pilot session | Charlotte Brown | 30% | 2026-09-07 | 2026-09-18
Collect employee feedback | William Taylor | 20% | 2026-09-14 | 2026-09-25
Revise materials | Amelia Carter | 10% | 2026-09-21 | 2026-10-02
Launch training program | Michael Wilson | 0% | 2026-09-28 | 2026-10-09
Evaluate results | Sarah Brown | 0% | 2026-10-12 | 2026-10-16
Marketing Campaign
Define campaign goals | James Wilson | 100% | 2026-08-03 | 2026-08-07
Research target audience | Emma Davis | 100% | 2026-08-10 | 2026-08-14
Create campaign concept | Olivia Carter | 90% | 2026-08-17 | 2026-08-28
Design advertisements | Noah Brown | 75% | 2026-08-24 | 2026-09-04
Prepare landing page | Ava Clark | 60% | 2026-08-31 | 2026-09-11
Schedule social posts | Liam Wilson | 45% | 2026-09-07 | 2026-09-18
Launch email campaign | Sophia Davis | 30% | 2026-09-14 | 2026-09-25
Launch paid advertising | Daniel Taylor | 20% | 2026-09-21 | 2026-10-02
Monitor campaign results | Michael Carter | 10% | 2026-09-28 | 2026-10-09
Prepare final campaign report | Sarah Miller | 0% | 2026-10-12 | 2026-10-16