## Blank Office Relocation Checkli
Office Relocation Checklist Template Designed by Spreadsheet Daddy
Task | Category | Owner | Due Date | Done | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Office Relocation Checklist Tem
Office Relocation Checklist Template Designed by Spreadsheet Daddy
Task | Category | Owner | Due Date | Done | Notes
Confirm new office lease | Planning | Office Manager | 2026-08-01 | TRUE | Lease agreement signed
Hire moving company | Logistics | Facilities Manager | 2026-08-05 | TRUE | Moving date confirmed
Create office relocation schedule | Planning | Project Manager | 2026-08-07 | TRUE | Shared with all departments
Notify employees of relocation | Communication | HR Manager | 2026-08-10 | TRUE | Company-wide email sent
Update company address with vendors | Administration | Office Administrator | 2026-08-12 | FALSE | Notify all service providers
Order packing supplies | Packing | Facilities Coordinator | 2026-08-15 | TRUE | Boxes, labels, and tape received
Label office furniture and equipment | Packing | Facilities Team | 2026-08-18 | FALSE | Use room numbers for labels
Back up company servers and files | IT | IT Manager | 2026-08-20 | TRUE | Full backup completed successfully
Disconnect computers and office equipment | IT | IT Support | 2026-08-22 | FALSE | Schedule after business hours
Transfer internet and phone services | Utilities | IT Manager | 2026-08-24 | FALSE | Installation appointment confirmed
Arrange furniture layout at new office | Facilities | Office Manager | 2026-08-26 | FALSE | Floor plan approved
Conduct final walkthrough of old office | Inspection | Project Manager | 2026-08-29 | FALSE | Verify all areas are cleared
Set up workstations in new office | Setup | Facilities Team | 2026-08-30 | FALSE | Install desks and monitors
Test internet, phones, and printers | IT | IT Support | 2026-08-31 | FALSE | Confirm all systems are operational
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE