## Blank Operational Readiness Che
Operational Readiness Checklist Template Designed by Spreadsheet Daddy
Readiness Item | Category | Assigned To | Priority | Due Date | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Operational Readiness Checklist
Operational Readiness Checklist Template Designed by Spreadsheet Daddy
Readiness Item | Category | Assigned To | Priority | Due Date | Completed | Notes
Confirm staff training is complete | People & Training | Emma Carter | High | 2026-08-20 | TRUE | All required staff completed training
Finalize operating procedures | Processes | James Wilson | High | 2026-08-20 | TRUE | Procedures approved
Verify system configuration | Technology | Sarah Miller | Critical | 2026-08-21 | FALSE | Final configuration review pending
Confirm user access permissions | Security | Michael Brown | High | 2026-08-21 | TRUE | Access levels reviewed
Prepare operational documentation | Documentation | Olivia Davis | Medium | 2026-08-22 | FALSE | Final documents being updated
Confirm support procedures | Support | Daniel Taylor | High | 2026-08-22 | TRUE | Support workflow documented
Test backup and recovery process | Business Continuity | Emily Clark | Critical | 2026-08-23 | FALSE | Recovery test scheduled
Review security controls | Security | Robert Lewis | Critical | 2026-08-23 | FALSE | Security review in progress
Confirm required approvals | Compliance | Amanda White | High | 2026-08-24 | FALSE | Final approval pending
Prepare launch communications | Communications | David Harris | Medium | 2026-08-24 | TRUE | Communication draft approved
Confirm monitoring and reporting | Technology | Sophia Martin | High | 2026-08-25 | FALSE | Monitoring setup underway
Verify support team coverage | Support | William Clark | High | 2026-08-25 | TRUE | Coverage confirmed
Review incident management process | Support | Mia Wilson | Medium | 2026-08-26 | FALSE | Process review scheduled
Confirm required equipment is available | Facilities | Ethan Davis | High | 2026-08-26 | TRUE | Equipment delivered
Review business continuity procedures | Business Continuity | Charlotte Brown | High | 2026-08-27 | FALSE | Updated plan awaiting review
Confirm compliance requirements | Compliance | Noah Taylor | Critical | 2026-08-27 | TRUE | Requirements reviewed
Complete operational documentation review | Documentation | Ava Martin | Medium | 2026-08-28 | FALSE | Final review pending
Conduct readiness walkthrough | Launch Readiness | Benjamin Wilson | High | 2026-08-28 | FALSE | Walkthrough scheduled
Document outstanding readiness issues | Launch Readiness | Amelia Davis | High | 2026-08-29 | FALSE | Open items being tracked
Complete final readiness approval | Launch Readiness | Henry Clark | Critical | 2026-08-30 | FALSE | Pending completion of outstanding items
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE