## Blank Product Launch Checklist
Product Launch Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Priority | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Product Launch Checklist Templa
Product Launch Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Priority | Completed | Notes
Finalize product specifications | Product Development | Emma Carter | 2026-08-10 | High | TRUE | Final specifications approved
Complete product quality testing | Testing | Daniel Wilson | 2026-08-11 | High | TRUE | All major tests passed
Review product packaging | Operations | Sarah Miller | 2026-08-12 | Medium | TRUE | Packaging design approved
Prepare product documentation | Content | Michael Brown | 2026-08-13 | High | FALSE | User guide awaiting final review
Create product landing page | Website | Olivia Davis | 2026-08-14 | High | TRUE | Page ready for final approval
Write launch announcement | Marketing | James Taylor | 2026-08-15 | High | FALSE | Draft in progress
Prepare social media content | Marketing | Ava Johnson | 2026-08-16 | Medium | FALSE | Posts scheduled for review
Create email launch campaign | Marketing | Noah Anderson | 2026-08-17 | High | TRUE | Email sequence completed
Prepare sales presentation | Sales | Sophia Martin | 2026-08-18 | Medium | FALSE | Sales team reviewing slides
Update pricing information | Sales | William Clark | 2026-08-18 | High | TRUE | Pricing approved by management
Train customer support team | Customer Support | Mia Wilson | 2026-08-19 | High | FALSE | Training session scheduled
Set up product analytics | Operations | Ethan Davis | 2026-08-20 | High | TRUE | Tracking events configured
Confirm inventory availability | Operations | Charlotte Brown | 2026-08-21 | High | TRUE | Initial inventory received
Test checkout and ordering process | Website | Benjamin Taylor | 2026-08-22 | High | FALSE | Final testing underway
Prepare launch-day communications | Public Relations | Amelia White | 2026-08-23 | Medium | FALSE | Announcement awaiting approval
Confirm launch date and schedule | Project Management | Henry Harris | 2026-08-24 | High | TRUE | Launch date confirmed
Review final launch checklist | Project Management | Evelyn Clark | 2026-08-25 | High | FALSE | Final review scheduled
Publish product across sales channels | Sales | Alexander Lewis | 2026-08-26 | High | FALSE | Scheduled for launch day
Monitor customer feedback after launch | Post-Launch | Harper Walker | 2026-08-29 | Medium | FALSE | Feedback review planned for first week
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE