## Blank Punch List Template
Punch List Template Designed by Spreadsheet Daddy
Item ID | Date Identified | Area/Location | Description | Category | Assigned To | Priority | Due Date | Status | Completion Date | Notes

## Punch List Template Example
Punch List Template Designed by Spreadsheet Daddy
Item ID | Date Identified | Area/Location | Description | Category | Assigned To | Priority | Due Date | Status | Completion Date | Notes
PL-1001 | 2026-08-01 | Main Entrance | Repair damaged door closer | Doors & Hardware | Mike Johnson | High | 2026-08-04 | Completed | 2026-08-03 | Door now closes properly
PL-1002 | 2026-08-01 | Reception Area | Touch up paint on north wall | Painting | Sarah Miller | Medium | 2026-08-06 | Completed | 2026-08-05 | Paint matched existing finish
PL-1003 | 2026-08-02 | Conference Room A | Replace damaged ceiling tile | Ceiling | James Carter | Medium | 2026-08-07 | In Progress | — | Replacement tile ordered
PL-1004 | 2026-08-02 | Restroom 1 | Repair leaking faucet | Plumbing | Robert Davis | High | 2026-08-04 | Completed | 2026-08-04 | Leak resolved
PL-1005 | 2026-08-03 | Hallway | Replace flickering light fixture | Electrical | Emily Wilson | High | 2026-08-05 | Completed | 2026-08-05 | New LED fixture installed
PL-1006 | 2026-08-03 | Break Room | Adjust cabinet door alignment | Carpentry | Kevin Taylor | Low | 2026-08-10 | Open | — | Cabinet door needs adjustment
PL-1007 | 2026-08-04 | Loading Dock | Repair damaged dock bumper | Exterior | Daniel Brown | High | 2026-08-08 | Assigned | — | Replacement bumper scheduled
PL-1008 | 2026-08-04 | Office 101 | Install missing electrical outlet cover | Electrical | Amanda Clark | Medium | 2026-08-06 | Completed | 2026-08-06 | Cover installed
PL-1009 | 2026-08-05 | Parking Lot | Repaint faded parking lines | Exterior | Brian Lewis | Medium | 2026-08-12 | In Progress | — | Striping crew scheduled
PL-1010 | 2026-08-05 | Stairwell | Secure loose handrail | Safety | Mike Johnson | High | 2026-08-06 | Completed | 2026-08-06 | Handrail secured
PL-1011 | 2026-08-06 | Conference Room B | Replace damaged floor tile | Flooring | Sarah Miller | Medium | 2026-08-11 | Open | — | Matching tile needs to be ordered
PL-1012 | 2026-08-06 | Warehouse | Repair damaged wall section | Drywall | James Carter | Medium | 2026-08-14 | Assigned | — | Materials available onsite
PL-1013 | 2026-08-07 | Employee Entrance | Adjust door that sticks when opening | Doors & Hardware | Robert Davis | High | 2026-08-09 | Completed | 2026-08-08 | Hinges adjusted
PL-1014 | 2026-08-07 | Restroom 2 | Replace cracked mirror | Fixtures | Emily Wilson | Medium | 2026-08-13 | Open | — | Replacement mirror requested
PL-1015 | 2026-08-08 | Office 105 | Patch small drywall hole | Drywall | Kevin Taylor | Low | 2026-08-15 | In Progress | — | Waiting for paint to dry
PL-1016 | 2026-08-08 | Mechanical Room | Label electrical panels | Safety | Daniel Brown | Medium | 2026-08-16 | Assigned | — | Labels being prepared
PL-1017 | 2026-08-09 | Exterior Wall | Seal gap around utility entrance | Exterior | Amanda Clark | High | 2026-08-12 | Open | — | Sealant required before inspection
PL-1018 | 2026-08-09 | Lobby | Replace scratched floor tile | Flooring | Brian Lewis | Low | 2026-08-18 | Open | — | Replacement material confirmed
PL-1019 | 2026-08-10 | Utility Room | Replace missing pipe insulation | HVAC | Mike Johnson | Medium | 2026-08-17 | In Progress | — | Insulation material ordered
PL-1020 | 2026-08-10 | Main Office | Test emergency lighting system | Electrical | Sarah Miller | High | 2026-08-14 | Pending Inspection | — | Final safety inspection required