## Blank RIF Checklist Template
RIF Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Priority | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## RIF Checklist Template Example
RIF Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Priority | Completed | Notes
Confirm business need for workforce reduction | Planning | HR Manager | 2026-08-03 | High | TRUE | Business rationale documented
Review affected departments and positions | Planning | HR Manager | 2026-08-04 | High | TRUE | Position list reviewed
Review applicable policies and requirements | Legal & Compliance | Legal Counsel | 2026-08-04 | High | TRUE | Internal requirements reviewed
Prepare proposed RIF plan | Planning | HR Director | 2026-08-05 | High | TRUE | Draft plan completed
Obtain leadership approval | Management Approval | Executive Team | 2026-08-06 | High | TRUE | Plan approved
Review employee selection criteria | Legal & Compliance | HR Manager | 2026-08-06 | High | TRUE | Criteria documented
Complete selection review | HR | HR Team | 2026-08-07 | High | TRUE | Selection process completed
Prepare required employee documentation | Documentation | HR Specialist | 2026-08-08 | High | FALSE | Documents under review
Prepare employee communication materials | Employee Communication | Communications Manager | 2026-08-08 | High | FALSE | Draft communications being finalized
Schedule employee notification meetings | Employee Communication | HR Manager | 2026-08-10 | High | FALSE | Meeting schedule pending
Review payroll and final compensation requirements | Payroll & Benefits | Payroll Manager | 2026-08-10 | High | FALSE | Final calculations pending
Review benefits information | Payroll & Benefits | Benefits Specialist | 2026-08-10 | Medium | FALSE | Benefits materials being prepared
Prepare internal communication plan | Employee Communication | Communications Manager | 2026-08-11 | Medium | FALSE | Internal announcement in progress
Review access termination process | IT & Access | IT Manager | 2026-08-11 | High | FALSE | Access list being prepared
Coordinate company property return | Equipment & Property | Office Manager | 2026-08-12 | Medium | FALSE | Return process prepared
Secure necessary personnel records | Documentation | HR Specialist | 2026-08-12 | High | FALSE | Records review scheduled
Complete employee notification process | Employee Communication | HR Team | 2026-08-13 | High | FALSE | Scheduled after final approval
Process payroll and benefits changes | Payroll & Benefits | Payroll Manager | 2026-08-14 | High | FALSE | Dependent on notification completion
Complete system access changes | IT & Access | IT Manager | 2026-08-14 | High | FALSE | Access changes scheduled
Conduct post-RIF review | Post-RIF Follow-Up | HR Director | 2026-08-20 | Medium | FALSE | Review outcomes and remaining workforce needs
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE