## Blank Requirements Gathering Te
Requirements Gathering Template Designed by Spreadsheet Daddy
Requirement ID | Requirement | Category | Source/Stakeholder | Priority | Assigned To | Due Date | Status | Acceptance Criteria | Notes

## Requirements Gathering Template
Requirements Gathering Template Designed by Spreadsheet Daddy
Requirement ID | Requirement | Category | Source/Stakeholder | Priority | Assigned To | Due Date | Status | Acceptance Criteria | Notes
REQ-1001 | User login with email and password | Functional | Project Manager | High | Alex Johnson | 2026-09-05 | Approved | Users can securely log in with valid credentials | Include password reset
REQ-1002 | Password reset functionality | Functional | Customer Support | High | Sarah Miller | 2026-09-08 | In Progress | Users can request and complete a password reset | Email confirmation required
REQ-1003 | Mobile-friendly interface | Usability | Marketing Team | High | James Wilson | 2026-09-12 | Approved | Pages display correctly on mobile devices | Test on major screen sizes
REQ-1004 | Customer profile management | Functional | Sales Team | Medium | Emily Davis | 2026-09-15 | In Progress | Users can view and update profile information | Include contact details
REQ-1005 | Search functionality | Functional | Operations Team | Medium | Michael Brown | 2026-09-18 | Proposed | Users can search records using keywords | Search results should load quickly
REQ-1006 | Role-based access controls | Security | IT Department | High | Daniel Clark | 2026-09-20 | Approved | Users only access features permitted for their role | Define admin and standard roles
REQ-1007 | Automated email notifications | Functional | Customer Support | Medium | Amanda Taylor | 2026-09-22 | In Progress | Notifications are sent after defined events | Create notification templates
REQ-1008 | Dashboard with key metrics | Reporting | Executive Team | High | Robert Wilson | 2026-09-25 | Approved | Dashboard displays agreed-upon performance metrics | Review metrics with leadership
REQ-1009 | Export reports to Excel | Reporting | Finance Team | Medium | Olivia Johnson | 2026-09-28 | Proposed | Users can export selected reports as Excel files | Preserve column formatting
REQ-1010 | Data backup process | Technical | IT Department | High | Chris Davis | 2026-09-30 | In Progress | Automated backups run according to schedule | Document recovery procedure
REQ-1011 | Audit trail for user activity | Security | Compliance Team | High | Laura Brown | 2026-10-02 | Under Review | User actions are recorded and searchable | Determine required retention period
REQ-1012 | Customer support contact form | Functional | Customer Support | Medium | Kevin Miller | 2026-10-05 | Approved | Customers can submit support requests successfully | Include category and priority fields
REQ-1013 | System response time under two seconds | Performance | IT Department | High | Rachel Wilson | 2026-10-08 | Proposed | Standard pages load within two seconds | Conduct performance testing
REQ-1014 | Multi-language support | Usability | Marketing Team | Low | Brian Taylor | 2026-10-10 | Needs Clarification | Users can select an available language | Confirm supported languages
REQ-1015 | Inventory tracking | Functional | Operations Manager | High | Jessica Clark | 2026-10-12 | In Progress | Inventory quantities update after transactions | Include low-stock alerts
REQ-1016 | Payment processing integration | Integration | Finance Team | High | Matthew Davis | 2026-10-15 | Under Review | Test payments process successfully and securely | Confirm payment provider
REQ-1017 | User activity reports | Reporting | Management Team | Medium | Nicole Johnson | 2026-10-18 | Proposed | Managers can generate activity reports by date | Include filtering options
REQ-1018 | Automated data validation | Technical | Data Team | Medium | Andrew Miller | 2026-10-20 | In Progress | Invalid entries are identified before submission | Define validation rules
REQ-1019 | Employee notification preferences | Usability | HR Department | Low | Megan Wilson | 2026-10-22 | Needs Clarification | Users can select which notifications they receive | Confirm available preferences
REQ-1020 | Final user acceptance testing | Testing | Project Sponsor | High | Thomas Brown | 2026-10-25 | Proposed | All critical acceptance tests pass before launch | Schedule final testing session