## Blank Rolling Action Item List
Rolling Action Item List Template Designed by Spreadsheet Daddy
Action Item ID | Action Item | Source | Assigned To | Priority | Date Added | Due Date | Status | Completion Date | Notes

## Rolling Action Item List Templa
Rolling Action Item List Template Designed by Spreadsheet Daddy
Action Item ID | Action Item | Source | Assigned To | Priority | Date Added | Due Date | Status | Completion Date | Notes
AI-1001 | Finalize Q3 project budget | Budget Meeting | Sarah Miller | High | 2026-08-01 | 2026-08-05 | Completed | 2026-08-04 | Approved by finance
AI-1002 | Send updated project timeline | Project Meeting | James Wilson | High | 2026-08-01 | 2026-08-06 | Completed | 2026-08-05 | Shared with stakeholders
AI-1003 | Review vendor proposals | Procurement Meeting | Olivia Davis | Medium | 2026-08-02 | 2026-08-09 | In Progress | — | Three proposals received
AI-1004 | Schedule team training session | Team Meeting | Michael Brown | Medium | 2026-08-02 | 2026-08-12 | Open | — | Confirm trainer availability
AI-1005 | Update customer contact database | Operations Review | Emily Clark | High | 2026-08-03 | 2026-08-10 | In Progress | — | Remove duplicate records
AI-1006 | Prepare monthly performance report | Management Meeting | Daniel Taylor | High | 2026-08-03 | 2026-08-08 | Completed | 2026-08-07 | Report distributed
AI-1007 | Confirm conference venue | Event Planning | Amanda Wilson | Medium | 2026-08-04 | 2026-08-15 | Pending | — | Waiting for venue response
AI-1008 | Review website analytics | Marketing Meeting | Robert Johnson | Low | 2026-08-04 | 2026-08-14 | Open | — | Review July traffic trends
AI-1009 | Update employee handbook | HR Meeting | Jessica Davis | Medium | 2026-08-05 | 2026-08-20 | In Progress | — | Policy updates underway
AI-1010 | Resolve outstanding IT tickets | IT Review | Brian Miller | High | 2026-08-05 | 2026-08-11 | In Progress | — | Five tickets remain
AI-1011 | Approve marketing campaign | Marketing Review | Laura Wilson | High | 2026-08-06 | 2026-08-13 | Pending | — | Awaiting leadership approval
AI-1012 | Order new office equipment | Operations Meeting | Kevin Brown | Medium | 2026-08-06 | 2026-08-16 | Open | — | Purchase order not submitted
AI-1013 | Complete customer survey analysis | Customer Review | Rachel Davis | Medium | 2026-08-07 | 2026-08-18 | In Progress | — | Survey responses being reviewed
AI-1014 | Schedule quarterly review meeting | Leadership Meeting | Andrew Clark | Low | 2026-08-07 | 2026-08-21 | Open | — | Coordinate executive schedules
AI-1015 | Update inventory records | Warehouse Meeting | Megan Taylor | High | 2026-08-08 | 2026-08-12 | In Progress | — | Physical count underway
AI-1016 | Review contract renewal terms | Legal Review | Thomas Wilson | High | 2026-08-08 | 2026-08-19 | Pending | — | Legal team reviewing terms
AI-1017 | Prepare onboarding materials | HR Planning | Nicole Brown | Medium | 2026-08-09 | 2026-08-22 | Open | — | New employee starts next month
AI-1018 | Follow up with prospective client | Sales Meeting | Chris Davis | High | 2026-08-09 | 2026-08-13 | Completed | 2026-08-12 | Follow-up call completed
AI-1019 | Review office safety checklist | Safety Meeting | Mark Johnson | Medium | 2026-08-10 | 2026-08-17 | Open | — | Inspection scheduled
AI-1020 | Prepare next team meeting agenda | Weekly Meeting | Sarah Miller | Low | 2026-08-10 | 2026-08-14 | Open | — | Include outstanding action items