## Blank Server Relocation Checkli
Server Relocation Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Priority | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Server Relocation Checklist Tem
Server Relocation Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Due Date | Priority | Completed | Notes
Create complete server inventory | Planning | Alex Morgan | 2026-08-10 | High | TRUE | Inventory includes servers, storage devices, and network equipment
Verify recent data backups | Backup | Emily Carter | 2026-08-10 | Critical | TRUE | Backup completed and restoration test verified
Document current server configurations | Documentation | Daniel Lee | 2026-08-11 | High | TRUE | Configuration records saved to project folder
Confirm new location power capacity | Power | Michael Brown | 2026-08-11 | High | TRUE | Power requirements confirmed with facilities team
Confirm network connections and IP addresses | Networking | Sarah Wilson | 2026-08-12 | Critical | FALSE | Network ports awaiting final confirmation
Label servers and cables | Inventory | James Taylor | 2026-08-12 | Medium | TRUE | Labels applied to all equipment
Schedule maintenance window | Planning | Olivia Martinez | 2026-08-13 | High | TRUE | Maintenance window approved for Saturday
Notify affected users and departments | Communication | Robert Davis | 2026-08-13 | Medium | TRUE | Notification sent to affected teams
Safely shut down servers | Shutdown | Sophia Clark | 2026-08-15 | Critical | FALSE | To be completed during maintenance window
Disconnect and package equipment | Equipment Removal | Benjamin Harris | 2026-08-15 | Critical | FALSE | Use protective packaging for all equipment
Transport equipment to new location | Transportation | William Anderson | 2026-08-15 | Critical | FALSE | Transportation scheduled with IT equipment vendor
Install servers in new racks | Installation | Mia Thompson | 2026-08-15 | High | FALSE | Rack positions documented in relocation plan
Reconnect power and network cables | Installation | Ethan Wilson | 2026-08-16 | Critical | FALSE | Follow equipment connection diagram
Start servers and verify hardware status | Testing | Grace Miller | 2026-08-16 | High | FALSE | Check hardware alerts after startup
Test network connectivity | Testing | Noah Carter | 2026-08-16 | Critical | FALSE | Verify internal and external connections
Verify applications and services | Testing | Ava Johnson | 2026-08-17 | Critical | FALSE | Confirm all required services are operational
Update server and network documentation | Documentation | Lucas Brown | 2026-08-18 | Medium | FALSE | Update records with new rack and network details
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE