## Blank Trade Show Checklist Temp
Trade Show Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Priority | Due Date | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Trade Show Checklist Template E
Trade Show Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Priority | Due Date | Completed | Notes
Register for the trade show | Event Planning | Emma Carter | Critical | 2026-08-20 | TRUE | Registration confirmed
Reserve booth space | Event Planning | James Wilson | Critical | 2026-08-20 | TRUE | Booth location confirmed
Design booth graphics | Booth Setup | Sarah Miller | High | 2026-08-22 | FALSE | Final design under review
Order promotional materials | Marketing Materials | Michael Brown | High | 2026-08-23 | FALSE | Order awaiting approval
Prepare product displays | Booth Setup | Olivia Davis | High | 2026-08-24 | FALSE | Display items being prepared
Arrange booth furniture | Booth Setup | Daniel Taylor | Medium | 2026-08-25 | FALSE | Furniture rental confirmed
Prepare brochures and flyers | Marketing Materials | Emily Clark | Medium | 2026-08-25 | TRUE | Materials sent to print
Arrange shipping to venue | Shipping & Logistics | Robert Lewis | High | 2026-08-26 | FALSE | Shipping pickup scheduled
Confirm staff schedule | Staffing | Amanda White | High | 2026-08-26 | TRUE | Staff assignments confirmed
Book staff travel | Travel | David Harris | High | 2026-08-27 | TRUE | Flights and hotel booked
Prepare staff briefing | Staffing | Sophia Martin | Medium | 2026-08-28 | FALSE | Briefing scheduled
Test laptops and presentation equipment | Technology | William Clark | High | 2026-08-28 | FALSE | Equipment testing pending
Prepare promotional giveaways | Promotional Items | Mia Wilson | Medium | 2026-08-29 | TRUE | Items packed
Prepare lead capture forms | Lead Management | Ethan Davis | High | 2026-08-29 | FALSE | Digital forms being tested
Pack booth supplies | Shipping & Logistics | Charlotte Brown | High | 2026-08-30 | FALSE | Packing list in progress
Confirm venue setup requirements | Booth Setup | Noah Taylor | High | 2026-08-30 | TRUE | Venue requirements confirmed
Complete booth setup | Booth Setup | Ava Martin | Critical | 2026-09-02 | FALSE | Setup planned for event day
Track leads during the event | Lead Management | Benjamin Wilson | High | 2026-09-03 | FALSE | Lead tracking assigned to sales team
Collect and organize event leads | Lead Management | Amelia Davis | High | 2026-09-04 | FALSE | To be completed after event
Follow up with qualified leads | Post-Event Follow-Up | Henry Clark | Critical | 2026-09-07 | FALSE | Follow-up campaign to begin after event
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE