## Blank Website Checklist Templat
Website Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Priority | Due Date | Completed | Notes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Website Checklist Template Exam
Website Checklist Template Designed by Spreadsheet Daddy
Task | Category | Assigned To | Priority | Due Date | Completed | Notes
Review website navigation | Planning | Emma Carter | High | 2026-08-20 | TRUE | Main navigation reviewed
Confirm page structure | Planning | James Wilson | High | 2026-08-20 | TRUE | Sitemap approved
Review homepage content | Content | Sarah Miller | High | 2026-08-21 | FALSE | Final copy review pending
Check images and media | Content | Michael Brown | Medium | 2026-08-21 | TRUE | Images optimized
Test contact forms | Testing | Olivia Davis | Critical | 2026-08-22 | FALSE | Form testing scheduled
Check internal links | Testing | Daniel Taylor | High | 2026-08-22 | TRUE | Broken links corrected
Test website on mobile devices | Testing | Emily Clark | Critical | 2026-08-23 | FALSE | Mobile testing in progress
Test website on major browsers | Testing | Robert Lewis | High | 2026-08-23 | FALSE | Browser testing pending
Review page titles | SEO | Amanda White | Medium | 2026-08-24 | TRUE | Titles reviewed
Review meta descriptions | SEO | David Harris | Medium | 2026-08-24 | FALSE | Several pages need updates
Check URL structure | SEO | Sophia Martin | Medium | 2026-08-24 | TRUE | URLs follow site structure
Verify analytics tracking | Analytics | William Clark | High | 2026-08-25 | FALSE | Tracking code needs verification
Check website loading speed | Performance | Mia Wilson | High | 2026-08-25 | FALSE | Performance review scheduled
Optimize large media files | Performance | Ethan Davis | Medium | 2026-08-26 | TRUE | Large images compressed
Review security settings | Security | Charlotte Brown | Critical | 2026-08-26 | FALSE | Security review pending
Verify SSL certificate | Security | Noah Taylor | Critical | 2026-08-26 | TRUE | Certificate active
Test website backups | Maintenance | Ava Martin | High | 2026-08-27 | FALSE | Backup restoration test pending
Review redirects | Development | Benjamin Wilson | Medium | 2026-08-27 | TRUE | Redirects tested
Complete final quality review | Launch | Amelia Davis | High | 2026-08-28 | FALSE | Final review pending
Approve website for launch | Launch | Henry Clark | Critical | 2026-08-29 | FALSE | Awaiting completion of open tasks
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE