## Blank Wedding Timeline Template
Wedding Timeline Template Designed by Spreadsheet Daddy
Task | Timeframe | Owner | Status | Notes

## Wedding Timeline Template Examp
Wedding Timeline Template Designed by Spreadsheet Daddy
Task | Timeframe | Owner | Status | Notes
Set wedding date and create budget | 12 months before | Couple | Completed | Budget approved and date confirmed
Book wedding venue | 11 months before | Couple | Completed | Contract signed with venue
Hire wedding planner | 10 months before | Couple | Completed | Planner selected
Choose wedding theme and colors | 9 months before | Couple | Completed | Theme: Elegant Garden Wedding
Book photographer and videographer | 9 months before | Planner | Completed | Deposit paid
Select caterer and menu | 8 months before | Couple | In Progress | Final tasting scheduled
Choose wedding dress and suits | 8 months before | Couple | Completed | Alterations planned
Create guest list | 7 months before | Couple | Completed | 120 guests confirmed
Send save-the-date invitations | 7 months before | Couple | Completed | Sent electronically
Book DJ and entertainment | 6 months before | Planner | Completed | Playlist discussion pending
Order wedding invitations | 5 months before | Couple | In Progress | Waiting for final design
Arrange flowers and decorations | 5 months before | Florist | In Progress | Color palette confirmed
Plan ceremony details | 4 months before | Couple | Not Started | Choose readings and vows
Book transportation | 3 months before | Planner | Not Started | Arrange guest shuttle
Finalize wedding menu | 3 months before | Caterer | In Progress | Confirm dietary requirements
Schedule dress fitting | 2 months before | Bride | In Progress | Final fitting appointment booked
Create seating chart | 1 month before | Couple | Not Started | Waiting for RSVP deadline
Confirm all vendors | 2 weeks before | Planner | Not Started | Review contracts and schedules
Prepare wedding day emergency kit | 1 week before | Maid of Honor | Not Started | Include essentials and supplies
Wedding rehearsal | 2 days before | Couple | Not Started | Practice ceremony flow
Final venue setup | Wedding day morning | Planner | Not Started | Decor and vendor setup
Bride and groom preparation | Wedding day | Couple | Not Started | Hair and makeup schedule
Ceremony begins | Wedding day 3:00 PM | Officiant | Not Started | Guests seated before start
Reception and dinner | Wedding day 5:00 PM | Catering Team | Not Started | Speeches and meal service
First dance and entertainment | Wedding day 7:00 PM | DJ | Not Started | Couple's first dance
Send thank-you messages | 1 week after | Couple | Not Started | Thank guests and vendors